## P3_1
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | DP:OK , expanding for other category following Label Design Approval from Japan side
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19 | Continue in FY19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01 | Continue in FY19
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
FY18 Conclusion:
+ Project Cost down is achieved but Project Improve Quality is not achieved.
+ Development time is still not increase because man-power not stable
FY19
+ Improve about analysis skill to make the good software at the 1st time
+ Training to improve develop skill for new members.
+ Sharing normal support technical with each others.
+ Stuy more new technology
[13 empty] | Develop time | Support time |  |  | Develop Time | Support time
[12 empty] | Before | 55% | 45% |  | Apr | 55% | 45%
[12 empty] | After | 70% | 30% |  | May | 60% | 40%
[16 empty] | Jun | 53% | 47%
[16 empty] | Jul | 56% | 44%
[16 empty] | Aug | 45% | 55%
[16 empty] | Sep | 60% | 40%
[16 empty] | Oct | 60% | 40%
[16 empty] | Nov | 50% | 50%
[16 empty] | Dec | 55% | 45%
[16 empty] | Jan | 52% | 48%
[16 empty] | Feb | 53% | 47%
[16 empty] | Mar | 52% | 48%
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |  |  |  |  | 651% | 549%
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21% |  |  |  |  | 54.25 | 45.75
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%
| Apr: 2019; May: 2020; Jun: 2021; Jul: 2022; Aug: 2023 |  |  |  | Develop time | Support time
Total | Apr: 81; May: 68; Jun: 84; Jul: 69; Aug: 57 |  |  | Before | 55% | 45%
Selected | Apr: 20; May: 14; Jun: 13; Jul: 16; Aug: 9 |  |  | After | 70% | 30%
Completed | Apr: 24; May: 26; Jun: 16; Jul: 22; Aug: 10
| Function | Old | New | 2 | menu
| Apr: GR; May: 12; Jun: 6; Jul: 9 |  | Common | Kitting FA | Goods receive | Kitting ouside | Free temp loacation | Storing
| Apr: Storing; May: 3; Jun: 1; Jul: 1 | OLD | 19 | 16 | 12 | 8 | 7 | 3
| Apr: Kitting; May: 16; Jun: 10; Jul: 10 | NEW | 4 | 9 | 9 | 4 | 4 | 2
| kitting outside | 8 | 8 | 2 | other
| Free temp | 7 | 7 | 4
| Common | 19 | 3 | 2
| Apr: Total; May: 65; Jun: 35 | [5 empty] | Old | New
[17 empty] | Total | 65 | 32
| Apr: Function; May: Old; Jun: New |  |  |  |  | Functions
| Total screen | 65 | 32

## Ita-Kona
ISG ITA-KONA ACTIVITY | [9 empty] | 30.125 | 16.25 | 16.125
Target | Increase Software Developing Time to get more cost down
Reduce OT outside plan
| Member name | Normal Support | Trouble Support | Develop | Line | Bar |  |  | Member name | Normal Support | Trouble Support | Develop | Line | Bar | Column1
Huong B | Member1 | 13% | 40% | 47% |  |  |  | OK | Huong B | 0% | 0% | 0% |  |  | 0%
Duong | Member2 | 12% | 6% | 81% |  |  |  | OK | Thao Tran | 65% | 10% | 25% |  |  | 100%
Lam | Member3 | 18% | 40% | 42% |  |  |  | OK | Lam | 45% | 20% | 35% |  |  | 100%
Thuy | Member4 | 17% | 31% | 52% |  |  |  | OK | Thuy | 30% | 45% | 25% |  |  | 100%
Hoa | Member5 | 50% | 26% | 24% |  |  |  | OK | Hoa | 68% | 26% | 6% |  |  | 100%
Huong N | Member6 | 10% | 16% | 74% |  |  |  | OK | Thao N | 83% | 10% | 7% |  |  | 100%
AVG |  | 20% | 26.5% | 53.33%
[8 empty] | OK | Quang | 74% | 20% | 6% |  |  | 100%
[8 empty] | OK | Chung | 30% | 60% | 10% |  |  | 100%
[9 empty] | AVG | 49.38% | 23.88% | 26.75% |  |  | 100%
[9 empty] | Member name | S | T | D
[9 empty] | Member1 | 0% | 0% | 0%
[9 empty] | Member name | S | T | D
[9 empty] | Member2 | 65% | 10% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member3 | 45% | 20% | 35%
[9 empty] | Member name | S | T | D
[9 empty] | Member4 | 30% | 45% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member5 | 68% | 26% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member6 | 83% | 10% | 7%
[9 empty] | Member name | S | T | D
[9 empty] | Member7 | 74% | 20% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member8 | 30% | 69% | 10%
[9 empty] | Member name | Normal Support | Trouble Support | Develop
[9 empty] | ISG | 49% | 24% | 27%
[9 empty] | Member name | Normal Support (S) | Trouble Support (T) | Develop (D)
[9 empty] | ISG Activity | 49% | 24% | 27%
| Huong B | Duong | Lam | Thuy | Hoa | Huong N | Tai | Quang | Chung
Normal Support | 13% | 12% | 18% | 17% | 50% | 10% | 81% | 94% | 82%
Trouble Support | 40% | 6% | 40% | 31% | 26% | 16% | 19% | 4% | 8%
Develop | 47% | 81% | 42% | 52% | 24% | 74% |  | 2% | 10%

## P3_draft
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN（PBX, DECT：ANS FA Prod Plan） | 0 | Common | 100% | 2018-08-18 | 2018-11-01 | 2019-02-01 | OK
9 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
11 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
12 | Mass upload Function for Scrap, Issue out | 0 | Common | 100% | 2019-01-19 | 2019-01-19 | 2019-01-19 | OK
13 | Auto Calculation of Raw material consumption | 0 | Common | 100% | 2018-11-18 | 2019-01-19 | 2019-01-19 | OK
14 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
15 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
17 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
18 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
19 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
20 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
21 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
22 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
23 (Urgent) | Control hopper | 0 | OCS,MCS | 100% | 2018-06-01 | 2018-12-01 | 2019-02-01 | OK
24(Urgent) | Modify printing label for all category | 0 | FA | 60% | 2018-10-18 | 2018-12-01 | 2018-12-01 | OK
25(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
26(Urgent) | Control Tray part | 0 | SMT | 80% | 2018-09-18 | 2018-12-01 | 2019-02-01 | OK
27(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45%

## P3
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK DP
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%

## Sheet1
Addition Request (Development team)
Seri | Item | CD
1
2
3
4
5

## Summary2
ISG FY2020 Projects Summary.
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 0 | 0 | 2 | 1 | 3 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 12
| Actual | Apr: 0; May: 0; Jun: 2; Jul: 1 | 3
Quality | Plan | 0 | 0 | 1 | 1 | 3 | 3 | 1 | 3 | 0 | 3 | 0 | 4 | 19
| Actual | Apr: 0; May: 0; Jun: 1; Jul: 2 | 3
FY2020 Itakona Achievement Monthly Summary. FY2020 Target Cost Down 74.3KUSD, Reduce HC 25 pax
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total |  | 48 | 5.76 | 138240000
Save Cost | [14 empty] | 37.8 | 960 | 115.2 | 2764800000 | bar: Apr to Jul
Improve Quality | bar: Apr to Jul
Amount Summary (K$/Y) | Plan | 0 | 0 | 0.4 | 0 | 7.6 | 0 | 6.86 |  |  | 13.5 |  | 21 | 49.36
| Actual | Apr: 0; May: 0; Jun: 0.4; Jul: 0 | 0.4
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 0.4 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 16.7 | ¡

## Summary2 (2)
ISG FY2021 Projects Summary.
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 0 | 1 | 3 | 1 | 0 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 18
| Actual | [12 empty] | 0 | 375
Quality | Plan | 0 |  | 2 | 2 | 1 | 1 | 1 |  | 1 | 1 | 0 |  | 9
| Actual | [12 empty] | 0
FY2021 Itakona Achievement Monthly Summary.
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Save Cost
Improve Quality
Amount Summary (K$/Y) | Plan |  | 0.05 | 32.73 | 18 | 0.67 | 4.5 | 0.42 | 0.51 | 33.44 |  | 19.35 | 6.12 | 115.79
| Actual | [12 empty] | 0
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 0 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 16.3 | ¡

## Summary
ISG PROGRESS ACTIVITY SUMMARY FY2021
Seri | Row Labels | CD (K$) | HC | Dept. | Result progress | Start | Completion Plan | Completion F/C | Remark
1 | PMG Improvement Auto BF and Follow up |  |  | PMG | 10% | 2021-04-01 | 2021-06-01
2 | Tranfer data IoT to SAP |  |  | SMT |  | 2021-05-01 | 2021-06-01
3 | QR Code for PCB of MW |  |  | SMT/FE |  | 2021-05-01 | 2021-07-01
4 | E–approve issue material in and out | 21.44 |  | ACS |  | 2021-07-01 | 2021-12-01
5 | MCS Free location |  | 2 | MCS |  | 2021-07-01 | 2021-12-01
6 | Verify Parts in FA automation line |  |  | FA |  | 2021-05-01 | 2021-07-01
7 | Link OQC weight check system with Production | 1.98 | 2 | OQC |  | 2021-11-01 | 2022-02-01
8 | Communication software: SMT line vs WH to order urgent materials | 5 |  | SMT/MCS/PUS |  | 2021-11-01 | 2022-02-01
9 | New version of Weight Check for checking more serial number for DECT | 4.6 |  | FA |  | 2022-01-01 | 2022-03-01
10 | Microwave Printing label | 1.205 |  | FA |  | 2021-12-01 | 2022-03-01
11 | Input NG lot-out q’ty on system for calculating delivery to avoid Inventory, deadstock/excess stock scrap | 0.66924 |  | PUS1 |  | 2021-06-01 | 2021-08-01
12 | Auto compare BOM/ECN btw SAP & Excel file | 0.507 |  | PMS |  | 2021-10-01 | 2021-11-01
13 | Improve T-code ZMV106 to download shortage items of all plan in one time | 0.3654 |  | PUS1 |  | 2021-12-01 | 2022-02-01
14 | Apply delivery control through SCM Navi with Panasonic trading | 0.56784 |  | PUS1
15 | Auto upload /check material master | 0.16224 |  | PMS |  | 2022-02-01 | 2021-03-01
16 | Creat T-Code auto download error list ( new part , specials control part ) | 0.1521 |  | COS |  | 2022-02-01 | 2021-03-01
17 | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | 0.12168 |  | PMS |  | 2021-11-01 | 2022-01-01
18 | Additional NG defect information (link…) on SAP | 0.1014 |  | PUS1
19 | Change inspection part in one RoHS group for next checking time | 0 |  | PQC |  | 2020-07-01 | 2020-09-01
20 | Setup same group for common part. | 0 | 3 | PQC |  | 2020-04-01 | 2020-06-01
21 | Create AQ2 confirmation for shipping using macro file | 0.732 |  | SCM |  | 2020-04-01 | 2020-06-01
22 | Upgrade token/USB to add function of signing in instead of hand signature & company stamp | 0.12 |  | SCM
23 | Fix "doc date" on invoice (zvv002) to only one format (dd-mmm-yy) | 0.054 |  | SCM |  | 2021-05-01 | 2021-05-01
24 | Build function on SAP to compare BOM with SMT program | 4.5 |  | SMT |  | 2021-07-01 | 2021-09-01
25 | New T_code for account leadger | 0 |  | ACS |  | 2020-11-01 | 2021-01-01
26 | Change G/L account 1550000000 (Finishgood) --> 1561010000 MERCHANDISE (COST OF PURCHASES) on IPC | 0 |  | ACS |  | 2020-10-01 | 2020-11-01
27 | Addition 10% VAT for verify material IPC request | 0 |  | ACS |  | 2020-12-01 | 2021-01-01
28 | Management sub-material | 14 |  | PROD |  | 2020-04-01 | 2020-06-01
29 | Control Custom INV in SAP matching DA/ EDI INV No. | 0.41574 |  | PUS1 |  | 2020-09-01 | 2020-10-01
30 | Study/support MM module | 0 |  | IT |  | 2020-04-01 | 2021-03-01
31 | VI01 Inventory count | 0 |  | PUS
32 | Freight Management | 0 | 3 | PUS1, PUS2, SCM |  | 2020-04-01 | 2020-07-01

## Activity all
|  | SECTION | Project Nam | CD | HC
1 | 1 | PMG | PMG Improvement Auto BF and Follow up |  |  | 2021-04-01 | 2021-06-01
2 | 2 | SMT | Tranfer data IoT to SAP |  |  | 2021-05-01 | 2021-06-01
3 | 3 | SMT/FE | QR Code for PCB of MW |  |  | 2021-05-01 | 2021-07-01
4 | 4 | ACS | E–approve issue material in and out | 21.44 |  | 2021-07-01 | 2021-12-01
5 | 5 | MCS | MCS Free location |  | 2 | 2021-07-01 | 2021-12-01
6 | 6 | FA | Verify Parts in FA automation line |  |  | 2021-05-01 | 2021-07-01
7 | 7 | OQC | Link OQC weight check system with Production | 1.98 | 2 | 2021-11-01 | 2022-02-01
8 | 8 | SMT/MCS/PUS | Communication software: SMT line vs WH to order urgent materials | 5 |  | 2021-11-01 | 2022-02-01
9 | 9 | FA | New version of Weight Check for checking more serial number for DECT | 4.6 |  | 2022-01-01 | 2022-03-01
10 | 10 | FA | Microwave Printing label | 1.205 |  | 2021-12-01 | 2022-03-01
1 | 11 | PUS1 | Input NG lot-out q’ty on system for calculating delivery to avoid Inventory, deadstock/excess stock scrap | 0.66924 |  | 2021-06-01 | 2021-08-01
2 | 12 | PMS | Auto compare BOM/ECN btw SAP & Excel file | 0.507 |  | 2021-10-01 | 2021-11-01
3 | 13 | PUS1 | Improve T-code ZMV106 to download shortage items of all plan in one time | 0.3654 |  | 2021-12-01 | 2022-02-01
4 | 14 | PUS1 | Apply delivery control through SCM Navi with Panasonic trading | 0.56784
5 | 15 | PMS | Auto upload /check material master | 0.16224 |  | 2022-02-01 | 2021-03-01
6 | 16 | COS | Creat T-Code auto download error list ( new part , specials control part ) | 0.1521 |  | 2022-02-01 | 2021-03-01
7 | 17 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | 0.12168 |  | 2021-11-01 | 2022-01-01
8 | 18 | PUS1 | Additional NG defect information (link…) on SAP | 0.1014
9 | 19 | PQC | Change inspection part in one RoHS group for next checking time | 0 |  | 2020-07-01 | 2020-09-01
10 | 20 | PQC | Setup same group for common part. | 0 | 3 | 2020-04-01 | 2020-06-01
11 | 21 | SCM | Create AQ2 confirmation for shipping using macro file | 0.732 |  | 2020-04-01 | 2020-06-01
12 | 22 | SCM | Upgrade token/USB to add function of signing in instead of hand signature & company stamp | 0.12
13 | 23 | SCM | Fix "doc date" on invoice (zvv002) to only one format (dd-mmm-yy) | 0.054 |  | 2021-05-01 | 2021-05-01
14 | 24 | SMT | Build function on SAP to compare BOM with SMT program | 4.5 |  | 2021-07-01 | 2021-09-01
15 | 25 | ACS | New T_code for account leadger | 0 |  | 2020-11-01 | 2021-01-01
16 | 26 | ACS | Change G/L account 1550000000 (Finishgood) --> 1561010000 MERCHANDISE (COST OF PURCHASES) on IPC | 0 |  | 2020-10-01 | 2020-11-01
17 | 27 | ACS | Addition 10% VAT for verify material IPC request | 0 |  | 2020-12-01 | 2021-01-01
18 | 28 | PROD | Management sub-material | 14 |  | 2020-04-01 | 2020-06-01
19 | 29 | PUS1 | Control Custom INV in SAP matching DA/ EDI INV No. | 0.41574 |  | 2020-09-01 | 2020-10-01
20 | 30 | IT | Study/support MM module | 0 |  | 2020-04-01 | 2021-03-01
21 | 31 | PUS | VI01 Inventory count | 0
22 | 32 | PUS1, PUS2, SCM | Freight Management | 0 | 3 | 2020-04-01 | 2020-07-01
|  |  |  | 56.6936 | 10