## Summary3
ISD FY2022 Projects Summary
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 2 | 1 | 1 | 2 | 10
| Actual | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 4
Quality | Plan | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 4 | 13
| Actual | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 7
FY2022 Itakona Achievement Monthly Summary
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Save Cost | bar: Jun to Sep; Nov to Feb
Improve Quality | bar: May to Sep; Nov; Feb
Amount Summary (K$/Y) | Plan | 0 | 0 | 5.4 | 0 | 0 | 18.7 | 0 | 3.1 | X | 50.8 | 1.5 | 2.1 | 82.7
| Actual | 0 | 0 | 0 | 8.5 | 0 | 20.5 | 0 | 0 |  | 5.7 | 0 |  | 29
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 29 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 45.3 | ¡
In Progress
O
Achieved
Non - Achieved
X

## Summary
ISD PROGRESS ACTIVITY SUMMARY FY2022
No | Row Labels | CD (K$) | HC | Section | Dept. | Result progress | Plan | Actual | Completion F/C | Remark
1 | Tooling Control Sheet | 5.4 | 0 | Dev | COS/LOG | 100 | 2022-06-01 | 2022-06-01 |  | Finished
2 | Auto transfer to SAP for outside plan | 0 | 1 | Dev & SAP | MCS | 75 | 2023-04-01 |  |  | On progress
3 | Printing area FTP configuration | 0 | 0.5 | Dev | PMD | 100 | 2023-02-01 | 2023-02-01 |  | Finished
4 | Auto Print Partcard preparation area | 1.5 | 0 | Dev | FA | 80 | 2023-02-01 |  |  | Testing (Move Feb->Mar)
5 | Auto Verify customs declaration data | 0 | 0.5 | Dev | SCM |  | 2023-03-01 |  |  | Cancel. Meeting & change the way to develop
6 | Auto Input tracking number to SAP for GR: Local, oversea | 1.7 | 0 | Dev | MCS | 100 | 2022-09-01 | 2022-09-01 |  | Finished
7 | Projector Traceability Optical Unit | 0 | 0 | Dev | PJ-FA | 100 | 2022-11-01 | 2022-11-01 |  | Finished
8 | Total Visualize System Module version 1 | 0 | 0 | Dev | All Depts | 100 | 2023-03-01 | 2023-03-01 |  | Finished
9 | Worker Management System Module: Manpower, Quality, Production | 0 | 0 | Dev | FA/QC | 90 | 2023-03-01 |  |  | Trial: Manpower, Prod, Quality module: MCW, DP
10 | PMD Warehouse management Upgrade | 0 | 0 | Dev | PMD |  | 2023-03-01 |  |  | Cancel. PIC ressign
11 | SCBU-Change Bill To Code from 00021631 to 00021878 | Quality | 0 | SAP | PSCD | 100 | 2022-05-01 | 2022-05-01 |  | Finished
12 | New type for Service part FOC (Free of charge Invoice) | Quality | 0 | SAP | PSCD | 100 | 2022-06-01 | 2022-06-01 |  | Finished
13 | Shipping advice analysis, Forecast report | 50.193 | 0 | SAP | PUS, PSCD | 100 | 2023-01-01 | 2023-01-01 |  | Finished ve1&2
14 | Management sub-material -Improvement (SA) | Quality | 0 | SAP | PROD | 100 | 2022-08-01 | 2022-08-01 |  | Finished
15 | New Inspection type for ROHs | Quality | 0 | SAP | QC | 100 | 2022-08-01 | 2022-08-01 |  | Finished
16 | New payment term for KABD | Quality | 0 | SAP | PSCD | 100 | 2022-07-01 | 2022-07-01 |  | Finished
17 | Add container number & SLOC for GR (SAP movement slip) | Quality | 0 | SAP | MCS, PUS1 | 100 | 2022-09-01 | 2022-09-01 |  | Finished
18 | e-Invoice : Send Invoice to FPT server (Call API) | 3.072 | 0 | SAP | ACD, PSCD | 100 | 2022-11-01 | 2022-11-01 |  | Finished
19 | Freight Management-Improvement (Add Accounting process) | 0.8 | 0 | SAP | PUS1, PUS2, SCM |  | 2022-12-01 |  |  | Cancel
20 | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD | 1.825 | 0 | SAP | PMS | 80 | 2023-03-01 |  |  | Developping
21 | SAP- suggest Sale based on inventory | Quality | 0 | SAP | PSCD, PUS | 90 | 2023-02-01 |  |  | Testing
22 | Document preperation for HANA | Quality | 0 | SAP | ISD | 80 | 2023-03-01 |  |  | Confirmed all programs status from each dept
23 | Install HANA (test environment) | Quality | 0 | SAP | ISD | 100 | 2022-12-01 | 2022-12-01
24 | Automation calculate valid date for ECN | 3.1 |  | Inovation | COS | 100 | 2023-02-23 | 2023-02-23
25 | Automation calculate excess stock after change ECN - Find out Amount remain old part | 0.02 |  | Inovation | PMS | 100 | 2023-02-23 | 2023-02-23
26 | Automation check ECN again after input ECN on SAP | 0.09 |  | Inovation | PMS | 100 | 2023-02-23 | 2023-02-23
27 | Auto check excess amount after changing to take action reduce inventory/loss cost & Inventory breakdown by reason | 0.8 |  | Inovation | PUS1, PUS2 | 10 | 2023-05-23
Addition requests
1 | FOSS- Print partcard changing | 0 | 0 | Dev | MCS | 100 | 2022-06-01 | 2022-06-01 |  | Finished
2 | DP Prevent Double ID, MAC ID | 0 | 0 | Dev | DP | 100 | 2022-07-01 | 2022-07-01 |  | Finished
3 | Debit Note, Creditnote system upgrade | 0 | 0 | Dev | All Depts | 100 | 2022-07-01 | 2022-07-01 |  | Finished
4 | Weight Check Projector for India destination | 0 | 0 | Dev | PJ-FA | 100 | 2022-10-01 | 2022-10-01 |  | Finished
5 | Elearning System V2 Expand | 18.8 | 0 | Dev | HRS | 100 | 2022-08-01 | 2022-08-01 |  | Finished
6 | Microwave OCS upgrade PLC to PC | 0 | 0 | Dev | MW-FA | 100 | 2022-08-01 | 2022-08-01 |  | Finished
7 | Issue Comercial Invoice and Issue E-Invoice following Tax |  |  | Dev | ACD, PROC | 100 |  |  |  | Finished
8 | Issue E-Invoice for Transportation Note floowing Tax |  |  | Dev | All Depts |  |  |  |  | Cancel
9 | Support AEO audit | 0 | 0 | SAP | All | 100 | 2022-06-01 | 2022-06-01 |  | Finished
10 | HULF management (for Background job) | 0 | 0 | SAP | ISD | 100 | 2022-09-01 | 2022-09-01 |  | Finished