## P3_1
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | DP:OK , expanding for other category following Label Design Approval from Japan side
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19 | Continue in FY19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01 | Continue in FY19
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
FY18 Conclusion:
+ Project Cost down is achieved but Project Improve Quality is not achieved.
+ Development time is still not increase because man-power not stable
FY19
+ Improve about analysis skill to make the good software at the 1st time
+ Training to improve develop skill for new members.
+ Sharing normal support technical with each others.
+ Stuy more new technology
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%

## Ita-Kona
ISG ITA-KONA ACTIVITY | [9 empty] | 30.125 | 16.25 | 16.125
Target | Increase Software Developing Time to get more cost down
Reduce OT outside plan
| Member name | Normal Support | Trouble Support | Develop | Line | Bar |  |  | Member name | Normal Support | Trouble Support | Develop | Line | Bar | Column1
Huong B | Member1 | 13% | 40% | 47% |  |  |  | OK | Huong B | 0% | 0% | 0% |  |  | 0%
Duong | Member2 | 12% | 6% | 81% |  |  |  | OK | Thao Tran | 65% | 10% | 25% |  |  | 100%
Lam | Member3 | 18% | 40% | 42% |  |  |  | OK | Lam | 45% | 20% | 35% |  |  | 100%
Thuy | Member4 | 17% | 31% | 52% |  |  |  | OK | Thuy | 30% | 45% | 25% |  |  | 100%
Hoa | Member5 | 50% | 26% | 24% |  |  |  | OK | Hoa | 68% | 26% | 6% |  |  | 100%
Huong N | Member6 | 10% | 16% | 74% |  |  |  | OK | Thao N | 83% | 10% | 7% |  |  | 100%
AVG |  | 20% | 26.5% | 53.33%
[8 empty] | OK | Quang | 74% | 20% | 6% |  |  | 100%
[8 empty] | OK | Chung | 30% | 60% | 10% |  |  | 100%
[9 empty] | AVG | 49.38% | 23.88% | 26.75% |  |  | 100%
[9 empty] | Member name | S | T | D
[9 empty] | Member1 | 0% | 0% | 0%
[9 empty] | Member name | S | T | D
[9 empty] | Member2 | 65% | 10% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member3 | 45% | 20% | 35%
[9 empty] | Member name | S | T | D
[9 empty] | Member4 | 30% | 45% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member5 | 68% | 26% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member6 | 83% | 10% | 7%
[9 empty] | Member name | S | T | D
[9 empty] | Member7 | 74% | 20% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member8 | 30% | 69% | 10%
[9 empty] | Member name | Normal Support | Trouble Support | Develop
[9 empty] | ISG | 49% | 24% | 27%
[9 empty] | Member name | Normal Support (S) | Trouble Support (T) | Develop (D)
[9 empty] | ISG Activity | 49% | 24% | 27%
| Huong B | Duong | Lam | Thuy | Hoa | Huong N | Tai | Quang | Chung
Normal Support | 13% | 12% | 18% | 17% | 50% | 10% | 81% | 94% | 82%
Trouble Support | 40% | 6% | 40% | 31% | 26% | 16% | 19% | 4% | 8%
Develop | 47% | 81% | 42% | 52% | 24% | 74% |  | 2% | 10%

## P3_draft
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN（PBX, DECT：ANS FA Prod Plan） | 0 | Common | 100% | 2018-08-18 | 2018-11-01 | 2019-02-01 | OK
9 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
11 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
12 | Mass upload Function for Scrap, Issue out | 0 | Common | 100% | 2019-01-19 | 2019-01-19 | 2019-01-19 | OK
13 | Auto Calculation of Raw material consumption | 0 | Common | 100% | 2018-11-18 | 2019-01-19 | 2019-01-19 | OK
14 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
15 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
17 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
18 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
19 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
20 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
21 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
22 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
23 (Urgent) | Control hopper | 0 | OCS,MCS | 100% | 2018-06-01 | 2018-12-01 | 2019-02-01 | OK
24(Urgent) | Modify printing label for all category | 0 | FA | 60% | 2018-10-18 | 2018-12-01 | 2018-12-01 | OK
25(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
26(Urgent) | Control Tray part | 0 | SMT | 80% | 2018-09-18 | 2018-12-01 | 2019-02-01 | OK
27(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45%

## P3
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK DP
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%

## Sheet1
Addition Request (Development team)
Seri | Item | CD
1
2
3
4
5

## Apr
ISG FY2019 Projects Summary.
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 1 | 2 | 3 | 1 | 2 | 3 | 0 | 2 | 1 | 3 | 2 | 5 | 25
| Actual | Apr: 2; May: 2; Jun: 3; Jul: 1; Aug: 3; Sep: 3; Oct: 0 | 14
| F/C | 1 | 2 | 3 | 1 | 2 | 3 | 0 | 2 | 1 | 3 | 2 | 5 | 25
Quality | Plan | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 3 | 0 | 1 | 2 | 12
| Actual | Apr: 1; May: 1; Jun: 0; Jul: 1; Aug: 2; Sep: 2; Oct: 2 | 9
| F/C | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 3 | 0 | 1 | 2 | 12
FY2019 Itakona Achievement Monthly Summary. FY2019 Target Save 289K$/Y
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Save Cost | bar: Apr to Sep
Improve Quality | bar: Apr to May; Aug to Oct
Amount Summary (K$/Y) | Plan | 0.4 | 50.1 | 8.3 | 35.3 | 5 | 91.6 | 0 | 14.4 | 50.8 | 1.9 | 8.5 | 23.1 | 289.4
| Actual | Apr: 0.9; May: 50.1; Jun: 68.6; Jul: 35.3; Aug: 5; Sep: 90 | 249.9
| F/C | 0.4 | 50.1 | 8.3 | 35.3 | 5 | 91.6 | 0 | 14.4 | 50.8 | 1.9 | 8.5 | 23.1 | 289.4
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 249.9 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 266.2 | ¡
Note on J5: Chung Nguyen Van: Nov LFC:1, Dec :3
Note on L14: MrChung: Add more 5.5K here

## Summary
ISG PROGRESS ACTIVITY SUMMARY (Nov- 2019)
Seri | Row Labels | CD (K$) | Dept. | Result progress | Start | Completion Plan | Completion F/C | Remark
1 | Issue Consolidated Sales Contract (PO) on SAP | 16.8 | FA | 100% | 2019-04-01 | 2019-05-30 | 2019-05-01 | OK
2 | Inventory PC improvement | 0 | ISG | 100% | 2019-04-01 | 2019-04-01 | 2019-04-01 | OK
3 | Post Difference by Storage Location | 24 | ACS | 100% | 2019-04-01 | 2019-05-01 | 2019-05-01 | OK
4 | Implement SVN to control source code | 0 | ISG | 100% | 2019-04-01 | 2019-05-01 | 2019-05-01 | OK
5 | Summarize Sub-Material | 0.4 | Production | 100% | 2019-04-01 | 2019-05-01 | 2019-05-01 | OK
6 | Pallet ID Deployment (SCN,PBX,DECT,HDC,FAX) | 0 | FA,SCM | 100% | 2019-04-01 | 2019-08-01 | 2019-08-01
7 | ECN (Change layout display, confirm all item for each model, email content) | 9.3 | FE | 70% | 2019-04-01 | 2020-03-01 | 2020-03-01
8 | EDI Invoice | 90 | Procurement | 70% | 2019-04-01 | 2019-09-01 | 2019-09-01
9 | QM Rolling | 4.2 | QC | 100% | 2019-04-01 | 2019-06-01 | 2019-06-01
10 | E-Tally Check Sheet | 33.6 | FA,SCM | 75% | 2019-05-01 | 2019-12-01 | 2019-12-01 | Tally sheet 1,2
11 | Line management system | 0 | ISG | 20% | 2019-04-01 | 2019-09-01 | 2019-09-01 | STOP
12 | Check part card by barcode scanning for DIP | 1.7 | DIP | 100% | 2019-06-01 | 2019-07-01 | 2019-07-01 | OK
13 | Implement Daily Quality Meeting Database | 2.9 | GQC | 100% | 2019-06-01 | 2019-06-01 | 2019-06-01 | OK
14 | Combine Inventory Report | 1.5 | ACS | 100% | 2019-06-01 | 2019-08-01 | 2019-08-01 | OK
15 | Training Contents by movie | 0.4 | ISG | 100% | 2019-06-01 | 2019-06-01 | 2019-06-01 | STOP
16 | Add more information in part card | 3.2 | SMT | 100% | 2019-07-01 | 2019-08-01 | 2019-08-01 | OK
17 | HS Code | 1.8 | Procurement | 100% | 2019-07-01 | 2019-08-01 | 2019-08-01
18 | Add container number & packing type on packing list | 0.1 | SCM | 100% | 2019-08-01 | 2019-08-01 | 2019-08-01
19 | Implement Tablet for FPQC dailly work | 50.8 | FPQC | 25% | 2019-08-01 | 2019-12-01 | 2019-12-01 | STOP
20 | Vendor code Standardization | 0 | Procurement |  | 2019-09-01 | 2019-09-01 | 2019-09-01 | STOP
21 | Improve PMG process by using Barcode system | 1.8 | PMG |  | 2019-09-01 | 2019-11-01 | 2019-11-01
22 | Master unit PCS or SET on invoice | 0 | SCM |  | 2019-10-01 | 2019-10-01 | 2019-10-01 | Change schedule
23 | OCR for SMT Material Label | 12.6 | MCS | 20% | 2019-10-01 | 2019-11-01 | 2019-11-01
24 | Urgent Treatment Sharing System | 8.4 | Procurement |  | 2019-11-01 | 2019-12-01 | 2019-12-01 | STOP
25 | Stationary Control System | 0 | BPS |  | 2019-11-01 | 2019-12-01 | 2019-12-01
26 | Improve Labor Cost Forecast | 0.2 | ACS |  | 2019-11-01 | 2020-01-01 | 2020-01-01
27 | Material Analyze Forecast Closing | 0.2 | ACS |  | 2019-11-01 | 2020-01-01 | 2020-01-01
28 | Purchase Info record with net price | 0 | Procurement |  | 2019-12-01 | 2019-12-01 | 2019-12-01
29 | QC Location Check | 8.4 | MCS |  | 2019-12-01 | 2020-02-01 | 2020-02-01 | STOP
30 | Make BOM for PAPVN | 1.5 | FE |  | 2019-12-01 | 2020-01-01 | 2020-01-01
31 | Upgrade IT Request Management System | 0 | ISG |  | 2019-12-01 | 2020-02-01 | 2020-02-01
32 | Control WIP PCB by Barcode | 0 | SMT |  | 2020-01-01 | 2020-02-01 | 2020-02-01 | STOP
33 | VMI Control Systemization | 4.9 | Procurement |  | 2020-01-01 | 2020-03-01 | 2020-03-01
34 | Verify Invoice for local vendor-+ | 0.1 | ACS |  | 2020-01-01 | 2020-02-01 | 2020-02-01
35 | Automatic Item master update from PDM system | 0.2 | PSCS |  | 2020-02-01 | 2020-03-01 | 2020-03-01
36 | Create tool for upload BOM PAPVN | 1.8 | Procurement |  | 2020-02-01 | 2020-03-01 | 2020-03-01
37 | Implement Tablet for OQC dailly work | 6.9 | OQC |  | 2020-02-01 | 2020-03-01 | 2020-03-01 | STOP
38 | Price Sanction | 0 | ACS |  | 2020-02-01 | 2020-03-01 | 2020-03-01
39 | EDI modification (PO, DA) |  | Procurement |  | 2019-10-01 | 2019-11-01 |  | Add
40 | Skip process(PBX,DP) |  | FA |  | 2019-10-01 | 2019-11-01 |  | Add
41 | New product project(projector) |  | FA |  | 2019-11-01 | 2020-01-01 |  | Add
42 | New product project(microwave) |  | FA |  | 2020-01-01 | 2020-03-01 |  | Add
43 | Security Gate project |  | Common |  | 2019-12-01 | 2020-01-01 |  | Add
44 | Traceability |  | Common |  | 2019-11-01 | 2020-03-01 |  | Add
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45%

## Sheet2
10%
20%
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
| Project No | 5 | 6 | 6 | 4 | 4 | 2 | 2 | 4 | 5 | 3 | 5 | 4
| Add Project | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 0 | 1
| Total project | 6 | 6 | 6 | 4 | 6 | 4 | 4 | 7 | 5 | 4 | 5 | 4
| Manpower | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Dev | bar: Apr to Jul
|  | 1 | 1 | 1