## P3_1
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | DP:OK , expanding for other category following Label Design Approval from Japan side
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19 | Continue in FY19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01 | Continue in FY19
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
FY18 Conclusion:
+ Project Cost down is achieved but Project Improve Quality is not achieved.
+ Development time is still not increase because man-power not stable
FY19
+ Improve about analysis skill to make the good software at the 1st time
+ Training to improve develop skill for new members.
+ Sharing normal support technical with each others.
+ Stuy more new technology
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%

## Ita-Kona
ISG ITA-KONA ACTIVITY | [9 empty] | 30.125 | 16.25 | 16.125
Target | Increase Software Developing Time to get more cost down
Reduce OT outside plan
| Member name | Normal Support | Trouble Support | Develop | Line | Bar |  |  | Member name | Normal Support | Trouble Support | Develop | Line | Bar | Column1
Huong B | Member1 | 13% | 40% | 47% |  |  |  | OK | Huong B | 0% | 0% | 0% |  |  | 0%
Duong | Member2 | 12% | 6% | 81% |  |  |  | OK | Thao Tran | 65% | 10% | 25% |  |  | 100%
Lam | Member3 | 18% | 40% | 42% |  |  |  | OK | Lam | 45% | 20% | 35% |  |  | 100%
Thuy | Member4 | 17% | 31% | 52% |  |  |  | OK | Thuy | 30% | 45% | 25% |  |  | 100%
Hoa | Member5 | 50% | 26% | 24% |  |  |  | OK | Hoa | 68% | 26% | 6% |  |  | 100%
Huong N | Member6 | 10% | 16% | 74% |  |  |  | OK | Thao N | 83% | 10% | 7% |  |  | 100%
AVG |  | 20% | 26.5% | 53.33%
[8 empty] | OK | Quang | 74% | 20% | 6% |  |  | 100%
[8 empty] | OK | Chung | 30% | 60% | 10% |  |  | 100%
[9 empty] | AVG | 49.38% | 23.88% | 26.75% |  |  | 100%
[9 empty] | Member name | S | T | D
[9 empty] | Member1 | 0% | 0% | 0%
[9 empty] | Member name | S | T | D
[9 empty] | Member2 | 65% | 10% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member3 | 45% | 20% | 35%
[9 empty] | Member name | S | T | D
[9 empty] | Member4 | 30% | 45% | 25%
[9 empty] | Member name | S | T | D
[9 empty] | Member5 | 68% | 26% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member6 | 83% | 10% | 7%
[9 empty] | Member name | S | T | D
[9 empty] | Member7 | 74% | 20% | 6%
[9 empty] | Member name | S | T | D
[9 empty] | Member8 | 30% | 69% | 10%
[9 empty] | Member name | Normal Support | Trouble Support | Develop
[9 empty] | ISG | 49% | 24% | 27%
[9 empty] | Member name | Normal Support (S) | Trouble Support (T) | Develop (D)
[9 empty] | ISG Activity | 49% | 24% | 27%
| Huong B | Duong | Lam | Thuy | Hoa | Huong N | Tai | Quang | Chung
Normal Support | 13% | 12% | 18% | 17% | 50% | 10% | 81% | 94% | 82%
Trouble Support | 40% | 6% | 40% | 31% | 26% | 16% | 19% | 4% | 8%
Develop | 47% | 81% | 42% | 52% | 24% | 74% |  | 2% | 10%

## P3_draft
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN（PBX, DECT：ANS FA Prod Plan） | 0 | Common | 100% | 2018-08-18 | 2018-11-01 | 2019-02-01 | OK
9 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
11 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
12 | Mass upload Function for Scrap, Issue out | 0 | Common | 100% | 2019-01-19 | 2019-01-19 | 2019-01-19 | OK
13 | Auto Calculation of Raw material consumption | 0 | Common | 100% | 2018-11-18 | 2019-01-19 | 2019-01-19 | OK
14 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
15 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
17 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
18 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
19 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
20 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
21 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
22 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
23 (Urgent) | Control hopper | 0 | OCS,MCS | 100% | 2018-06-01 | 2018-12-01 | 2019-02-01 | OK
24(Urgent) | Modify printing label for all category | 0 | FA | 60% | 2018-10-18 | 2018-12-01 | 2018-12-01 | OK
25(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
26(Urgent) | Control Tray part | 0 | SMT | 80% | 2018-09-18 | 2018-12-01 | 2019-02-01 | OK
27(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45%

## P3
ISG PROGRESS ACTIVITY SUMMARY (Mar - 2019)
Seri | Row Labels | CD (K$) | Dept. | Jun Result progress | Start | Completion Plan | Completion F/C | Remark
1 | “100% Barcode” Pallet ID | 34 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK DP
2 | M-Traceability (Lot No. for critical Material) | 0 | Common | 100% | 2018-04-18 | 2019-03-01 | 2019-03-01 | OK
3 | M-Traceability (Repair area) | 0 | SMT,FA | 10% | 2018-09-18 | 2018-12-18 | 2019-03-01 | Replace SMT add request
4 | M-Traceability (Link to OQC) | 0 | Common | 5% | 2018-10-18 | 2018-12-18 | 2019-03-01 | Reschedule because some urgent request
5 | M-Traceability（Trace back: PC, PBX) | 0 | Common | 100% | 2018-10-18 | 2019-03-01 | 2019-03-01 | OK
6 | M-Traceability（Trace forward: PC, PBX） | 0 | Common | 5% | 2018-10-18 | 2019-03-01 | 2019-03-01 | Replace by urgent item
7 | ECN link to FA production plan (PBX, DECT） | 0 | Common | 100% | 2018-07-01 | 2018-11-01 | 2019-01-31 | OK
8 | ECN link to SMT scheduler | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
9 | Portal login synchronize global AD | 0 | Common | 0% | 2019-01-19 | 2019-03-19 | 2019-03-19 | Replace by urgent item
10 | Vender Code Standardization | 0 | Common | 0% | 2018-12-01 | 2019-03-19 | 2019-02-19
11 | EDI Invoice / Barcode for oversea suppliers | 54 | Procurement | 70% | 2018-04-18 | 2019-03-01 | 2019-03-01
12 | Weight check support new model (PBX:115) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
13 | Weight check support new model (CPT:1) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
14 | Weight check support new model (DP:53) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
15 | Weight check support new model (SCN:34) | 0 | FA | 100% | 2018-07-01 | 2019-03-01 | 2019-03-01 | OK
16 | E-Tally Check sheet for SP | 1 | PSCS | 0% | 2018-11-18 | 2019-02-19 | 2019-05-19 | Reschedule because some urgent request
17 | Upload Production Plan by Category, not by BD | 1.5 | PSCS | 100% | 2018-04-18 | 2018-06-01 | 2019-03-01 | OK
18 | Just transfer auto for Daily Production Plan | 2.9 | PSCS | 100% | 2018-05-01 | 2019-03-01 | 2019-03-01 | OK
19 | QM master function | 9.3 | Common | 80% | 2018-08-18 | 2018-12-18 | 2018-12-18
20(Urgent) | Weight check for TEV | 0 | FA | 10% | 2018-10-18 | 2019-03-19 | 2019-06-19 | High Priority
21(Urgent) | Production result daily for TEV | 0 | FA | 0% | 2019-01-19 | 2019-03-19 | 2019-06-19 | High Priority
31 | Deploy PCTM | 0 | Common | 100% |  | 2018-06-01 | 2018-12-01 | OK
Conclusion:
+ Develop time is reduced because shortage develop members (under recruiting)
+ Follow up each support case of members to reduce support time
+ Sharing normal support technical with each others.
+ Training to improve develop skill for new members.
+ Reschedule with sections and try to catch up total KPI Plan
Comparation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Develop | 40% | 38% | 36% | 45% | 37% | 26% | 27% | 28% | 32% | 29% | 31% | 35%
Trouble Support | 40% | 20% | 19% | 25% | 32% | 30% | 24% | 19% | 22% | 18% | 24% | 21%
Normal Support | 20% | 42% | 45% | 30% | 31% | 44% | 49% | 53% | 46% | 53% | 45% | 44%

## Sheet1
Addition Request (Development team)
Seri | Item | CD
1
2
3
4
5

## Summary2
ISG FY2020 Projects Summary.
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 0 | 0 | 2 | 1 | 3 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 12
| Actual | Apr: 0; May: 0; Jun: 2; Jul: 1 | 3
Quality | Plan | 0 | 0 | 1 | 1 | 3 | 3 | 1 | 3 | 0 | 3 | 0 | 4 | 19
| Actual | Apr: 0; May: 0; Jun: 1; Jul: 2 | 3
FY2020 Itakona Achievement Monthly Summary. FY2020 Target Cost Down 74.3KUSD, Reduce HC 25 pax
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total |  | 48 | 5.76 | 138240000
Save Cost | [14 empty] | 37.8 | 960 | 115.2 | 2764800000 | bar: Apr to Jul
Improve Quality | bar: Apr to Jul
Amount Summary (K$/Y) | Plan | 0 | 0 | 0.4 | 0 | 7.6 | 0 | 6.86 |  |  | 13.5 |  | 21 | 49.36
| Actual | Apr: 0; May: 0; Jun: 0.4; Jul: 0 | 0.4
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 0.4 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 16.7 | ¡

## Summary2 (2)
ISG FY2020 Projects Summary.
Quantity Summary |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
Cost down | Plan | 0 | 1 | 2 | 1 | 3 | 0 | 2 | 1 | 1 | 1 | 0 | 2 | 14
| Actual | 0 | 1 | 2 | 1 | 2 | 2 | 1 | 1 |  |  |  |  | 10
Quality | Plan | 0 | 0 | 1 | 1 | 3 | 3 | 1 | 0 | 0 | 3 | 0 | 4 | 16 | 12 |  | 20
| Actual | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 0 |  |  |  |  | 9
[15 empty] | 312 |  | 520 | 0.832
FY2020 Itakona Achievement Monthly Summary. | [19 empty] | 10800 | 180 | 0.72
Month |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total |  |  |  | 48 |  | 5.76 |  | 138240000
Save Cost | [14 empty] | 37.8 |  |  | 960 |  | 5.76 |  | 138240000 | bar: Apr to Nov
Improve Quality | [17 empty] | 4152 |  | 15.57 | 519 | bar: Apr to Oct
Amount Summary (K$/Y) | Plan | 0 | 0.2 | 0.4 | 0 | 5.76 | 0 | 0.72 | 0.83 |  |  |  |  | 7.91 | [5 empty] | 35.57
| Actual | 0 | 0.2 | 0.4 | 0 | 5.76 | 46.694 | 0.72 | 0.83 |  |  |  |  | 54.604
[16 empty] | 124.56 |  | 2781 | 11.124
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y) | Result
Project |  | Apr: 54.604 | ¡
Other Activity |  | Apr: 16.3 | ¡
Total |  | Apr: 70.904 | ¡
[16 empty] | 14523 |  |  | 2600

## Summary
ISG PROGRESS ACTIVITY SUMMARY
Seri | Row Labels | CD (K$) | Dept. | Result progress | Start | Completion Plan | Completion F/C | Remark
1 | One Plant for SMT | 20pax | MCS, SMT, PUS | 100% | 2020-04-01 | 2020-07-01 |  | Develop completed, waiting SMT inventory
2 | Improve Labor Cost Forecast | 0.2 | ACS | 100% | 2020-04-01 | 2020-06-01 |  | Completed
3 | Material Analyze Forecast Closing | 0.2 | ACS | 100% | 2020-04-01 | 2020-06-01 |  | Completed
4 | EDI Invoice (25 remains: New Vendor, some Vendor ony have 1 PO or long time order ) |  | PUS | 100% | 2020-04-01 | 2021-03-01 |  | Completed
5 | BOM for AP-PDM in SAP | 1 | PUS, FE, COS | 90% | 2020-05-01 | 2020-08-01 |  | Completed
6 | Issue document to pdf file from SAP without spool request |  | SCM | 100% | 2020-05-01 | 2020-08-01 |  | Completed
7 | Mass creating Packing list |  | SCM | 100% | 2020-05-01 | 2020-05-01 |  | Completed
8 | Calculate FC & Scrap list | 0.8 | PUS |  | 2020-06-01 | 2020-08-01 |  | Replace
9 | Upload Just transfer |  | PCS | 100% | 2020-07-01 | 2020-11-01 |  | Completed
10 | Etally sheet for Oversea Service Part |  | FA | 100% | 2020-06-01 | 2020-07-01 |  | Completed
11 | Compare Serial outer and inner PBX's |  | FA | 100% | 2020-06-01 | 2020-08-01 |  | Completed
12 | Projector Label printing |  | FA | 100% | 2020-06-01 | 2020-08-01 |  | Completed
13 | Projector quality improvement MEBD |  | FA | 100% | 2020-06-01 | 2020-09-01 |  | Completed
14 | Security Gate |  | Common | 60% | 2020-06-01 | 2021-01-01 |  | Log file to server
15 | OR part changing tool to avoid any mistake & lost time as manual process |  | PUS | 100% | 2020-07-01 | 2020-11-01 |  | Completed
16 | Tool for monthly scrap. Inventory, Forcast report making |  | PUS | 100% | 2020-07-01 | 2020-08-01 |  | Completed
17 | MCS kitting situation auto reflect | 1pax | MCS | 100% | 2020-07-01 | 2020-08-01 |  | Completed
18 | G/L account posting for Vendor | 0.7 | ACS |  | 2020-08-01 | 2020-10-01 |  | Replace
19 | Auto GR & BF for PMG |  | PMG | 50% | 2020-08-01 | 2020-01-01
20 | SOX |  | IT | 100% | 2020-08-01 | 2020-09-01 |  | Completed
21 | Microwave traceability |  | FA | 80% | 2020-08-01 | 2021-01-01 |  | Following
22 | PMG improvement | 3pax | PMG | 50% | 2020-08-01 | 2021-01-01 |  | Test GR, plan & kitting
23 | Compare PDM and Mouting Program | 35.57 | SMT | 100% | 2020-08-01 | 2020-09-01 |  | Completed
24 | Daily plan making automation for some new cat |  | PCS | 100% | 2020-09-01 | 2020-11-01 |  | Completed
25 | CREATE TENTATIVE PACKING LIST (R3) BY UPLOAD SHIPPING SCHEDULE. CSV FILE |  | SCM | 35% | 2020-09-01 | 2020-12-01
26 | SAP ECN change valid auto calculate |  | Cost | 30% | 2020-09-01 | 2021-01-01
27 | MCS auto Transfer by Reservation number |  | MCS | 60% | 2020-09-01 | 2020-12-01
28 | Auto transfer kitting data to SAP | 1pax | MCS | 90% | 2020-09-01 | 2020-12-01 |  | Waiting SAP
29 | Video making for IT Training course |  | Common |  | 2020-09-01 | 2021-03-01 |  | Replace
30 | Master unit PCS or SET on invoice |  | SCM | 100% | 2020-10-01 | 2020-11-01 |  | Completed
31 | Free location | 2pax | QC,MCS | 15% | 2020-10-01 | 2021-03-01
32 | RFID inventory | 12.6 | PE |  | 2020-11-01 | 2021-03-01 |  | Change
33 | Input NG lot-out q’ty on system for calculating delivery to avoid Inventory, deadstock/excess stock scrap |  | PUS |  | 2020-12-01 | 2021-03-01
34 | Inventory PC automatically |  | ISG |  | 2021-01-01 | 2021-03-01
35 | Control Custom INV in SAP matching DA/ EDI INV No. |  | PUS |  | 2021-02-01 | 2021-03-01
36 | Prices sanction |  | ACS |  | 2020-11-01 | 2020-12-01
37 | Printing Label for Dect |  | FA |  | 2020-12-01 | 2020-12-01
38 | Weight check for Dect |  | FA |  | 2020-12-01 | 2020-12-01
39 | Printing Label for DP |  | FA |  | 2020-12-01 | 2020-12-01
40 | Weight check for DP |  | FA |  | 2020-12-01 | 2020-12-01
41 | ECN Valid Date changing |  | FE |  | 2021-02-01 | 2021-02-01

## Sheet2
10%
20%
[11 empty] | MCS, SMT, PUS | FA
[11 empty] | ACS | MCS
[11 empty] | ACS | FA
[11 empty] | PUS, FE, COS | FA
[11 empty] | PCS | FA
[11 empty] | SCM | MCS
[11 empty] | SCM | Common
| DECT | DP | PBX | SCN | PROJ | MW | Others | Daily time (H) | PIC need |  | PUS | FA
Before | 8 | 8 | 5 | 3 | 3 | 3 | 2 | 32 | 4 |  | PUS | PMG
After PCS centralization | 6 | 6 | 3 | 2 | 2.5 | 2.5 | 2 | 24 | 3 |  | SCM | QC,MCS
After IT-lization | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 1 |  | MCS | PE
ISG
Common
8