## SAP_Jun
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-05-27 | 2022-06-03 | 2022-06-09 | 2022-06-16 | 2022-06-23
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | [12 empty] | Compliant | bar: Apr to May
Result | bar: Apr to May
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan | [12 empty] | Compliant |  | May shipment OK V2Q test continue |  | next shipment not clear in June | next month | next month | bar: May to Jun
Result
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Lam | Chinh | Plan | [12 empty] | 50193 |  | Tuesday test again (only loacl supplier) if OK, GO-LIVE and next function | Testing continue | test do by PUR but not yet reply meeting on Sunday | oversea additional function test local OK | Cos member check | bar: Apr to Jun; Oct to Nov
Result
| SAP | 4 | PUS, | Forecast report | New | Hong | Plan | bar: Oct to Jan
Result
| SAP | 5 | All | Support AEO audit | Hoa/Lam | Hoa | Plan | [15 empty] | Support | Support | Support | PO pdf file can not get by archive depend on Qty we will care | bar: Apr to Jun
Result
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan | [12 empty] | Quality |  | meeting: Next week All process test department leader will decide final operation | not yet start | meeting cancel | waitng schedule | PR can not delete find reason next week fix |  | Section | request | chosen | bar: Jun to Aug
Result
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan | [12 empty] | Quality |  |  |  | Japan Idea -> QC reject consider other method | not yet | suggest Manual change to QC other 3 items finish by supporting |  | PMS | 8 | 2 | bar: Jun to Aug
[7 empty] | Result | [20 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan | [16 empty] | make maual (teramoto) | Sunday install | Study |  | PSCD | 8 | 5 | bar: Jun to Sep
[7 empty] | Result | [20 empty] | PUS | 12 | 5
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan | [12 empty] | Compliant |  |  |  | analyze this month need | next week start | this month/next month how to care |  | SMT | 1 | 0 | bar: Jun to Jul
[7 empty] | Result | [20 empty] | QM | 1 | 1
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan | [12 empty] | Compliant | bar: Jul to Sep
Result
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan | [12 empty] | 3072 |  |  |  | API test doing format | SAP link with API OK collecting data (Vietnamese) | collecting data/vietnamese | =4$/1h*8h/1day*24day*4month | bar: Aug to Nov
[7 empty] | Result | [12 empty] | &Compliant
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [12 empty] | 800 | [6 empty] | (27/05 : ACD will send Costdown) | bar: Oct to Dec
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [12 empty] | 1825 | bar: Dec to Mar
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [12 empty] | reduce Inventory |  |  |  |  | I will contact PSCD Thuy san | next week I will discuss with Hayashi san | bar: Dec to Feb
Result
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [12 empty] | Policy | bar: Oct to Mar
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [12 empty] | Policy | bar: Sep to Dec
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job |  |  |  | Oct: SAP TOTAL(PLAN) | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) |  |  |  | Oct: SAP TOTAL(RESULT) | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan | [14 empty] | Ask Linh san WM: 2file upload RF:A/B modify same as WM BOM upload -> solution by Lam san adding A/B side column and upload 1 file only -->not yet schedule -->after SA |  | finish
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [18 empty] | discuss again calculate by rate
Result
Plan
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan | [14 empty] | will discuss with Toan san Team
Result

## SAP_July
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-06-23 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | 1 | 1 | [10 empty] | Compliant
[7 empty] | Result | 1 | 1
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan |  | 1 | 1 | [9 empty] | Compliant |  | next month | monitor | monitor | next week investigation | already apply V1P
Result | bar: 2022-07-01 to 2022-07-08; 2022-07-22
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Lam | Chinh | Plan | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 50193 |  | Cos member check | test delay for audit keep until finish e-invoice | oversea OK/loca MW OK local other test continue master setting matter | local supplier test again 1 supplier have 2 route in master | test not yet finish | rule change -> program modify OK, testing
Result | bar: 2022-07-01 to 2022-07-29
| SAP | 4 | PUS, | Forecast report | New | Hong | Plan | [6 empty] | 1 | 1 | 1 | 1
Result
| SAP | 5 | All | Support AEO/HQ audit | Hoa/Lam | Hoa | Plan | 1 | 1 | 1 | [11 empty] | PO pdf file can not get by archive depend on Qty we will care | Old PO support by Excel Macro | procurement submit old PO list again | continue supporting
Result | bar: 2022-07-01 to 2022-07-15
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality |  | PR can not delete find reason next week fix | Hoa san testing | test finish Procurement want to use MD04 but reject | test summary meeting need after audit | next week meeting | not yet meeting |  | Section | request | chosen
Result | bar: 2022-07-08 to 2022-07-29
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality |  | 2022-06-23: suggest Manual change to QC other 3 items finish by supporting; 2022-07-01: complete |  | PMS | 8 | 2
[7 empty] | Result | [21 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan |  |  | 1 | 1 | 1 | 1 | [8 empty] | Study | next study again remote desktop confirm to Hayashi san | study confirm remote desktop | studying | remote desktop setting for Teramoto OK | file trigger testing V2Q, continue study |  | PSCD | 8 | 5
[7 empty] | Result | [21 empty] | PUS | 12 | 5 | bar: 2022-07-08 to 2022-07-22
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan |  |  | 1 | 1 | [8 empty] | Compliant |  | this month/next month how to care | finish and supporting |  | additional request come thuy san make schedule | after e-invoice | after e-invoice |  | SMT | 1 | 0
[7 empty] | Result | [21 empty] | QM | 1 | 1 | bar: 2022-07-15 to 2022-07-22
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan |  |  |  | 1 | 1 | 1 | [6 empty] | Compliant |  |  |  | Development FOSS auto GR | waiting schedule Dev & MCS | Dev | DEV
Result | bar: 2022-07-08 to 2022-07-22
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 3072 |  | collecting data/vietnamese | V2Q testing | V1P testing upload excel file function | test with PSCD summarize result 5 issue | & matter exchange rate OK | exchange rate no display prduction env. Now asking | =4$/1h*8h/1day*24day*4month
[7 empty] | Result | [12 empty] | &Compliant | bar: 2022-07-01 to 2022-07-29
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [6 empty] | 1 | 1 | 1 |  |  |  | 800 | [7 empty] | (27/05 : ACD will send Costdown)
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [8 empty] | 1 | 1 | 1 | 1 | 1825
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [8 empty] | 1 | 1 | 1 |  | reduce Inventory |  | 2022-06-23: next week I will discuss with Hayashi san; 2022-07-01: continue consider
Result
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | Policy
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | Policy
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job | [9 empty] | SAP TOTAL(PLAN) | [5 empty] | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) | [9 empty] | SAP TOTAL(RESULT) | [5 empty] | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [14 empty] | discuss again calculate by rate | no news | will make schedule | no news | complete | complete
Result | bar: 2022-07-08 to 2022-07-15
|  |  |  | SA for IPO |  |  | Plan |  |  |  | 1 | [12 empty] | next week finish | IT TEST OK waiting user test | test OK and go-live | test OK and go-live
Result | bar: 2022-07-08 to 2022-07-15
|  |  |  | EDI for PV |  |  | Plan | [14 empty] | 2022-07-15: setting by ePro/GITP member; 2022-07-22: wait 2 Aug; 2022-07-29: wait 2 Aug
Result | bar: 2022-07-15 to 2022-07-22
|  |  |  | EDI for MEBD |  |  | Plan | [14 empty] | 2022-07-15: complete; 2022-07-22: complete; 2022-07-29: complete
Result
|  |  |  | EDI for ATLAS |  |  | Plan | [14 empty] | 2022-07-22: i/V testing
Result
|  |  |  | EDI for GENIOS |  |  | Plan | [14 empty] | 2022-07-22: mei fong san
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan
Result

## SAP_Aug
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-08-31
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | [12 empty] | Compliant | bar: Apr to May
Result | bar: Apr to May
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan | [12 empty] | Compliant | bar: May to Jun
Result
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Lam | Chinh | Plan | [12 empty] | 50193 |  | testing and modify | Local using oversea additional 2 case today testing and OK. Next week all finish | start | Sep restart | Sep restart | bar: Apr to Jun; Oct to Nov
Result
| SAP | 4 | PUS, | Forecast report | New | Hong | Plan | bar: Oct to Jan
Result
| SAP | 5 | All | Support AEO/HQ audit | Hoa/Lam | Hoa | Plan | bar: Apr to Jun
Result
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan | [12 empty] | Quality |  |  | not yet | continue TEST next week requirement com | Test within Aug PUR Sep Golive | Test Next week |  | Section | request | chosen | bar: Jun to Aug
Result
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan | [12 empty] | Quality | [7 empty] | PMS | 8 | 2 | bar: Jun to Aug
[7 empty] | Result | [20 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan | [14 empty] | study | study continue | in Aug meeting | Next Monday test calculate efficiency | Next week |  | PSCD | 8 | 5 | bar: Jun to Sep
[7 empty] | Result | [20 empty] | PUS | 12 | 5
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan | [12 empty] | Compliant |  |  | changed 2 forms invoice, packing list, more 2 type next week | finish all |  |  |  | SMT | 1 | 0 | bar: Jun to Jul
[7 empty] | Result | [20 empty] | QM | 1 | 1
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan | [12 empty] | Compliant |  |  | DEV | DEV | Develop start | next week test | bar: Jul to Sep
Result
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan | [12 empty] | 3072 |  | SAP invoice need change | they using finish | finish but master matter | Excel file problem tomorrow modify | V2Q alrady waiting OK by email then V1P transport | =4$/1h*8h/1day*24day*4month | bar: Aug to Nov
[7 empty] | Result | [12 empty] | &Compliant
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [12 empty] | 800 | [6 empty] | (27/05 : ACD will send Costdown) | bar: Oct to Dec
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [12 empty] | 1825 | bar: Dec to Mar
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [12 empty] | reduce Inventory |  |  | Sep Oct meeting |  |  | Oct discussion | bar: Dec to Feb
Result
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [12 empty] | Policy | bar: Oct to Mar
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [12 empty] | Policy | bar: Sep to Dec
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job |  |  |  | Oct: SAP TOTAL(PLAN) | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) |  |  |  | Oct: SAP TOTAL(RESULT) | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [14 empty] | complete | complete | complete | complete
Result
|  |  |  | SA for IPO |  |  | Plan | [14 empty] | test OK and go-live | test OK and go-live | test OK and go-live | test OK and go-live | bar: Jul
Result
|  |  |  | EDI for PV |  |  | Plan | [14 empty] | testing PV waiting | ask again next week | PV side doing Sep continue | Sep | Sep
Result
|  |  |  | EDI for MEBD |  |  | Plan | [14 empty] | complete | complete | complete | complete
Result
|  |  |  | EDI for ATLAS(PRJ) |  |  | Plan | [15 empty] | 2022-09-07 | RO need registration | RO no use compare PSNV PO/supplier Recive status
Result
|  |  |  | EDI for GENIOS |  |  | Plan
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan
Result

## SAP_Sep
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-31 | 2022-09-16 | 2022-09-23
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | 1 | 1 | [10 empty] | Compliant
[7 empty] | Result | 1 | 1
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan |  | 1 | 1 | [9 empty] | Compliant
Result
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Lam | Chinh | Plan | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 50193 |  | testing and modify | Local using oversea additional 2 case today testing and OK. Next week all finish | start | Sep restart | next Monday meeting procurement discussing | we send kick off request no answer
Result | bar: 2022-08-05 to 2022-08-31
| SAP | 4 | PUS, | Forecast report | New | Hong | Plan | [6 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 2022-09-23: module by module separate 2 developer
Result
| SAP | 5 | All | Support AEO/HQ audit | Hoa/Lam | Hoa | Plan | 1 | 1 | 1
Result
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality |  |  | not yet | continue TEST next week requirement com | Test Next week | testing again | testing additional function |  | Section | request | chosen
Result | bar: 2022-08-12 to 2022-08-31
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality | [8 empty] | PMS | 8 | 2
[7 empty] | Result | [21 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan |  |  | 1 | 1 | 1 | 1 | [8 empty] | study | study continue | in Aug meeting | Next week | Tuesday afternoon | V2Q test finish V1P setting with PSNM |  | PSCD | 8 | 5
[7 empty] | Result | [21 empty] | PUS | 12 | 5 | bar: 2022-08-12 to 2022-08-31
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan |  |  | 1 | 1 | [8 empty] | Compliant |  | 2022-08-12: changed 2 forms invoice, packing list, more 2 type next week; 2022-08-19: finish all |  | SMT | 1 | 0
[7 empty] | Result | [21 empty] | QM | 1 | 1 | bar: 2022-08-12 to 2022-08-19
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan |  |  |  | 1 | 1 | 1 | [6 empty] | Compliant |  |  | DEV | DEV | next week test | prepare for golive | near golive
Result | bar: 2022-08-19 to 2022-08-31
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 3072 |  | SAP invoice need change | they using finish | finish but master matter | V2Q alrady waiting OK by email then V1P transport |  |  | =4$/1h*8h/1day*24day*4month
[7 empty] | Result | [12 empty] | &Compliant | bar: 2022-08-05 to 2022-08-31
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [6 empty] | 1 | 1 | 1 |  |  |  | 800 |  | 2022-09-23: SCM : finish 10 Oct check actual data ACC : PUR/SCM data compare | (27/05 : ACD will send Costdown)
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [8 empty] | 1 | 1 | 1 | 1 | 1825
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [8 empty] | 1 | 1 | 1 |  | reduce Inventory |  | 2022-08-12: Sep Oct meeting; 2022-08-31: Oct discussion
Result | bar: 2022-08-12; 2022-08-31
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | Policy |  | 2022-09-23: ALL T-code listup
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | Policy |  | 2022-09-16: t-code review sep
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job | [9 empty] | SAP TOTAL(PLAN) | [5 empty] | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) | [9 empty] | SAP TOTAL(RESULT) | [5 empty] | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | SA for IPO |  |  | Plan |  |  |  | 1 | [10 empty] | 2022-08-05: test OK and go-live; 2022-08-12: test OK and go-live; 2022-08-19: test OK and go-live
Result
|  |  |  | EDI for PV |  |  | Plan | [14 empty] | testing PV waiting | ask again next week | PV side doing Sep continue | Sep | no answer | PV side setting trouble
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for MEBD |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | EDI for ATLAS(PRJ) |  |  | Plan | [14 empty] | 2022-08-12: 2022-09-07; 2022-08-19: RO need registration; 2022-09-16: close
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for GENIOS |  |  | Plan
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan | [14 empty] | 2022-09-23: pass to Toan san team
Result
|  |  |  | e-invoice (PAPVN) |  |  | Plan | [14 empty] | 2022-09-23: get
Result
|  |  |  | Blue Yonder |  |  | Plan
Result
|  |  |  | e-invoice (IPC/VND) |  |  | Plan
Result

## SAP_Oct
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-31 | 2022-09-23 | 2022-10-21
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | 1 | 1 | [10 empty] | Compliant
[7 empty] | Result | 1 | 1
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan |  | 1 | 1 | [9 empty] | Compliant
Result
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Trung | Chinh | Plan | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 50193 |  | testing and modify | Local using oversea additional 2 case today testing and OK. Next week all finish | start | Sep restart | we send kick off request no answer | FS confirming next monda confirm
Result | bar: 2022-08-05 to 2022-08-31
| SAP | 4 | PUS, | Forecast report | Lam | Hong | Plan | [6 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 2022-09-23: module by module separate 2 developer; 2022-10-21: same as SA
Result
| SAP | 5 | All | Support AEO/HQ audit | Hoa/Lam | Hoa | Plan | 1 | 1 | 1
Result
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality |  |  | not yet | continue TEST next week requirement com | Test Next week | testing additional function | testing (program very slow read big table) |  | Section | request | chosen
Result | bar: 2022-08-12 to 2022-08-31
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality | [8 empty] | PMS | 8 | 2
[7 empty] | Result | [21 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan |  |  | 1 | 1 | 1 | 1 | [8 empty] | study | study continue | in Aug meeting | Next week | V2Q test finish V1P setting with PSNM | Batch file testing |  | PSCD | 8 | 5
[7 empty] | Result | [21 empty] | PUS | 12 | 5 | bar: 2022-08-12 to 2022-08-31
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan |  |  | 1 | 1 | [8 empty] | Compliant |  | 2022-08-12: changed 2 forms invoice, packing list, more 2 type next week; 2022-08-19: finish all |  | SMT | 1 | 0
[7 empty] | Result | [21 empty] | QM | 1 | 1 | bar: 2022-08-12 to 2022-08-19
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan |  |  |  | 1 | 1 | 1 | [6 empty] | Compliant |  |  | DEV | DEV | next week test | near golive | finish
Result | bar: 2022-08-19 to 2022-08-31
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 3072 |  | SAP invoice need change | they using finish | finish but master matter | V2Q alrady waiting OK by email then V1P transport |  |  | =4$/1h*8h/1day*24day*4month
[7 empty] | Result | [12 empty] | &Compliant | bar: 2022-08-05 to 2022-08-31
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [6 empty] | 1 | 1 | 1 |  |  |  | 800 |  | 2022-09-23: SCM : finish 10 Oct check actual data ACC : PUR/SCM data compare; 2022-10-21: not yet start | (27/05 : ACD will send Costdown)
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [8 empty] | 1 | 1 | 1 | 1 | 1825
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [8 empty] | 1 | 1 | 1 |  | reduce Inventory |  | 2022-08-12: Sep Oct meeting; 2022-08-31: Oct discussion
Result | bar: 2022-08-12; 2022-08-31
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | Policy |  | 2022-09-23: ALL T-code listup
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | Policy
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job | [9 empty] | SAP TOTAL(PLAN) | [5 empty] | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) | [9 empty] | SAP TOTAL(RESULT) | [5 empty] | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | SA for IPO |  |  | Plan |  |  |  | 1 | [10 empty] | 2022-08-05: test OK and go-live; 2022-08-12: test OK and go-live; 2022-08-19: test OK and go-live
Result
|  |  |  | EDI for PV |  |  | Plan | [14 empty] | testing PV waiting | ask again next week | PV side doing Sep continue | Sep | PV side setting trouble
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for MEBD |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | EDI for ATLAS(PRJ) |  |  | Plan | [14 empty] | 2022-08-12: 2022-09-07; 2022-08-19: RO need registration
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for GENIOS |  |  | Plan
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan | [14 empty] | 2022-09-23: pass to Toan san team
Result
|  |  |  | e-invoice (PAPVN) |  |  | Plan | [14 empty] | 2022-09-23: get
Result
|  |  |  | Blue Yonder |  |  | Plan
Result
|  |  |  | e-invoice (IPC/VND) |  |  | Plan
Result

## SAP_Nov
B&A> | Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-31 | 2022-09-23 | 2022-10-21 | 2022-11-18
| SAP | 1 | PSCD | SCBU-Change Bill To Code from 00021631 to 00021878 | Hoa | PSCD | Plan | 1 | 1 | [10 empty] | Compliant
[7 empty] | Result | 1 | 1
| SAP | 2 | PSCD | New type for Service part FOC (Free of charge Invoice) | Hoa | Linh | Plan |  | 1 | 1 | [9 empty] | Compliant
Result
| SAP | 3 | PUS, PSCD | Shipping advice analysis | Trung | Chinh | Plan | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 50193 |  | testing and modify | Local using oversea additional 2 case today testing and OK. Next week all finish | start | Sep restart | we send kick off request no answer | FS confirming next monda confirm | vendor confirm function SCMNavi/1 more
Result | bar: 2022-08-05 to 2022-08-31
| SAP | 4 | PUS, | Forecast report | Lam | Hong | Plan | [6 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 2022-09-23: module by module separate 2 developer; 2022-10-21: same as SA; 2022-11-18: stop
Result
| SAP | 5 | All | Support AEO/HQ audit | Hoa/Lam | Hoa | Plan | 1 | 1 | 1
Result
| SAP | 6 | PROD | Management sub-material -Improvement (SA) | Lam | Dung | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality |  |  | not yet | continue TEST next week requirement com | Test Next week | testing additional function | testing (program very slow read big table) | OK / finish checking waitinf FA check consumption master |  | Section | request | chosen
Result | bar: 2022-08-12 to 2022-08-31
| SAP | 7 | QC | New Inspection type for ROHs | Hoa | Nhung PQC | Plan |  |  | 1 | 1 | 1 | [7 empty] | Quality | [9 empty] | PMS | 8 | 2
[7 empty] | Result | [22 empty] | COS | 6
| SAP | 8 | ISD | HULF management (for Background job) | Hoa | ALL | Plan |  |  | 1 | 1 | 1 | 1 | [8 empty] | study | study continue | in Aug meeting | Next week | V2Q test finish V1P setting with PSNM | Batch file testing | studying again |  | PSCD | 8 | 5
[7 empty] | Result | [22 empty] | PUS | 12 | 5 | bar: 2022-08-12 to 2022-08-31
| SAP | 9 | PSCD | New payment term for KABD | Hoa, Lam | ACD/PSCD | Plan |  |  | 1 | 1 | [8 empty] | Compliant |  | 2022-08-12: changed 2 forms invoice, packing list, more 2 type next week; 2022-08-19: finish all |  | SMT | 1 | 0
[7 empty] | Result | [22 empty] | QM | 1 | 1 | bar: 2022-08-12 to 2022-08-19
| SAP | 10 | MCS, PUS1 | Add container number & SLOC for GR (SAP movement slip) | Hoa | Nguyen, Trang | Plan |  |  |  | 1 | 1 | 1 | [6 empty] | Compliant |  |  | DEV | DEV | next week test | near golive | finish
Result | bar: 2022-08-19 to 2022-08-31
| SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Lam | ACD/PSCD | Plan |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 3072 |  | 2022-08-05: SAP invoice need change; 2022-08-12: they using finish; 2022-08-19: finish but master matter; 2022-08-31: V2Q alrady waiting OK by email then V1P transport | =4$/1h*8h/1day*24day*4month
[7 empty] | Result | [12 empty] | &Compliant | bar: 2022-08-05 to 2022-08-31
| SAP | 12 | PUS1, PUS2, SCM | Freight Management-Improvement (Add Accounting process) | Lam | X.Phương PUS, Linh SCM | Plan | [6 empty] | 1 | 1 | 1 |  |  |  | 800 |  | 2022-09-23: SCM : finish 10 Oct check actual data ACC : PUR/SCM data compare; 2022-10-21: not yet start; 2022-11-18: not yet start | (27/05 : ACD will send Costdown)
Result
| SAP | 13 | PMS | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) | New | Yến | Plan | [8 empty] | 1 | 1 | 1 | 1 | 1825
Result
| SAP | 14 | PSCD, PUS | SAP- suggest Sale based on inventory | Lam | ALL | Plan | [8 empty] | 1 | 1 | 1 |  | reduce Inventory |  | 2022-08-12: Sep Oct meeting; 2022-08-31: Oct discussion
Result | bar: 2022-08-12; 2022-08-31
| SAP | 15 | ISD | Document preperation for HANA | ALL | ALL | Plan | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | Policy |  | 2022-09-23: ALL T-code listup
Result
| SAP | 16 | ISD | Install HANA (test environment) | Hoa | ALL | Plan | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | Policy
Result
|  |  |  | Consider to reduce "repetitive work" and not necessary job | [9 empty] | SAP TOTAL(PLAN) | [5 empty] | 55890 | 0
|  |  |  | Create PI, Send PO, receive Sales order, check error (upload Inbound,…), check DA from e-Procurement) | [9 empty] | SAP TOTAL(RESULT) | [5 empty] | 0 | 0
|  |  | Procurement,FE | Extend Function Auto convert BOM PAPVN | Lam |  | Plan
Result
|  |  |  | Microwave SCRAP |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | SA for IPO |  |  | Plan |  |  |  | 1 | [10 empty] | 2022-08-05: test OK and go-live; 2022-08-12: test OK and go-live; 2022-08-19: test OK and go-live
Result
|  |  |  | EDI for PV |  |  | Plan | [14 empty] | testing PV waiting | ask again next week | PV side doing Sep continue | Sep | PV side setting trouble
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for MEBD |  |  | Plan | [14 empty] | 2022-08-05: complete; 2022-08-12: complete; 2022-08-19: complete
Result
|  |  |  | EDI for ATLAS(PRJ) |  |  | Plan | [14 empty] | 2022-08-12: 2022-09-07; 2022-08-19: RO need registration
Result | bar: 2022-08-12; 2022-08-31
|  |  |  | EDI for GENIOS |  |  | Plan
Result
Plan
Result
|  |  |  | Auto Convetr MW for Sub material OR use |  |  | Plan | [14 empty] | 2022-09-23: pass to Toan san team
Result
|  |  |  | e-invoice (PAPVN) |  |  | Plan | [14 empty] | 2022-09-23: get
Result
|  |  |  | Blue Yonder |  |  | Plan
Result
|  |  |  | e-invoice (IPC/VND) |  |  | Plan
Result

## DEV_Jun
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC |  | 2022-05-27 | 2022-06-03 | 2022-06-09 | 2022-06-16 | 2022-06-26
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | [12 empty] | 5.4 |  |  | Testing, Some revise | test so so OK format not match-> training | waitng answer next week go-live | Next Monday go-live schedule fix | go-live but no use | bar: Apr to Jun
[5 empty] | Binh | Result | bar: Apr to May
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | [15 empty] | Change from Box by box to model by model | testing with PIC | MCS PIC test Sun or Mon make schedule for Ennouji san test | A4 part card inline ->new testing from today | go-live from 1 July | bar: Apr to Jun
Result | bar: Apr to May
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan | [15 empty] | 2 format already fix start develop | next week start | discussion with PE | developing next week test with PE 1st step | 1st time test do prepare not enough | bar: May to Jul
[5 empty] | Tan | Result | bar: Jun
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan | [15 empty] | VB6 version now | Phong san | review current version | Debit complete payment request (VND) before USD | testing mid of july test | bar: Jun to Jul
Result | bar: Jun
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh | Quyen | Plan | [15 empty] | for special destination | bar: Sep to Oct
Result
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan | [17 empty] | transfer complete status check function | GA not response | GA | bar: Jun to Aug
Result | bar: Jun
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan | [15 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | next week start 1.how to collect data 2.how to import to DB automatically 3.recheck data in Weight check | Minh san & Dao san support | prepare for production restart 28 June | bar: Jun to Aug
[5 empty] | Son | Result | bar: Jun
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan | bar: Jul to Oct
Result
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan | bar: Jul to Mar
Result
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh | Hai | Plan | [15 empty] | at first apply MEBD | bar: Jul to Mar
Result
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [13 empty] | 1 | 6 | bar: Oct to Jan
Result
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | bar: Jan to Mar
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [13 empty] | 0.5 |  | DEV/INFRA | bar: Oct to Dec
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [12 empty] | 1.5 | bar: Dec to Feb
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [13 empty] | 0.5 | bar: Jan to Mar
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan | [12 empty] | 1.7 |  | 1.5 | 1728 | bar: Aug to Sep
Result
DEV | 17 |  |  |  |  | Plan
Result
[7 empty] | 4 | 5 | 10 | 7 | 6 | 5 | 6 | 4 | 5 | 6 | 5 | 4
[7 empty] | Oct: DEV TOTAL(PLAN) | 8.6 | 2
DEV TOTAL(RESULT)
DEV | 18 |  | Weight Check no detect shipment log file |  |  | Plan | [19 empty] | investigation (Operation/Osftware) monitor 1 week
Result
DEV | 19 |  | e-invoice for issue in/out |  |  | Plan | [19 empty] | issue in/out modify 1st week of July transportataion note also need
Result
DEV | 20 |  | e-invoice for transportation note |  |  | Plan
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_July
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC |  | 2022-05-27 | 2022-06-03 | 2022-06-26 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | Testing, Some revise | test so so OK format not match-> training | go-live but no use | same | finish
[5 empty] | Binh | Result | 1 | 1 | bar: 2022-06-03; 2022-07-01 to 2022-07-08
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [12 empty] | Change from Box by box to model by model | testing with PIC | go-live from 1 July | go-live | finish
[6 empty] | Result | 1 | 1 | bar: 2022-06-03; 2022-07-01 to 2022-07-08
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2 format already fix start develop | next week start | 1st time test do prepare not enough | testing line production and OK next week meeting | 1 additional request / finish next week test | testing | testing | next Monday Ask PE status
[5 empty] | Tan | Result |  |  | 1 | bar: 2022-05-27 to 2022-06-03; 2022-07-01 to 2022-07-29
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [11 empty] | VB6 version now | Phong san | testing mid of july test | develop complete waiting user test | go-live already
[6 empty] | Result |  |  | 1 | bar: 2022-07-01 to 2022-07-08
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination; 2022-07-15: study; 2022-07-22: study review by Hien san; 2022-07-29: next week 1st step test
Result | bar: 2022-07-15 to 2022-07-22
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [12 empty] | GA | GA | making script | HR &GA | no news | no news
[6 empty] | Result |  |  | 1 | bar: 2022-07-01 to 2022-07-29
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | prepare for production restart 28 June | next Monday meeting with PE | asking Sakaguchi san | yesterday meeting Next Monday PE finish and test start | PE still making | PE not yet combine program finish
[5 empty] | Son | Result |  |  | 1 | bar: 2022-05-27 to 2022-06-03; 2022-07-01 to 2022-07-22
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  | 1 | 1 | 1 | 1 | [8 empty] | 2022-07-15: receive concept only; 2022-07-22: plannning; 2022-07-29: August concept check test after that line
Result | bar: 2022-07-15
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 2022-07-15: discuss key member; 2022-07-22: Next Monday kick off; 2022-07-29: next week PIC discuss
Result | bar: 2022-07-15; 2022-07-29
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  |  |  | plannning | after audit kick off | plan kick off | Long san: next week meeting again
Result | bar: 2022-07-15
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [6 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 | 6
Result
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [6 empty] | 1 | 1 | 1 |  |  |  |  | 0.5 |  | 2022-05-27: DEV/INFRA
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728
Result
DEV | 17 |  |  |  |  | Plan
Result
[7 empty] | 4 | 5 | 10 | 7 | 6 | 5 | 6 | 4 | 5 | 6 | 5 | 4
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
DEV TOTAL(RESULT)
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [17 empty] | investigation (Operation/software) monitor 1 week |  | finally no problem | finally no problem | finally no problem | finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [13 empty] | issue in/out modify 1st week of July transportataion note also need | modify OK next Monday test | testing & revise complete next week complete | accounting & procurement test 1 more request / next week test again | all request complete test this week finish | already finish 2 Aug go-live
Result | bar: 2022-07-15 to 2022-07-29
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [15 empty] | 2022-07-08: FPT will send API Document for transportation; 2022-07-15: after issue in/out start; 2022-07-29: after issue in/out complete
Result | bar: 2022-07-15
DEV | 21 |  | seven eleven | Hien |  | Plan | [15 empty] | 2022-07-15: next week decision; 2022-07-29: complete
Result | bar: 2022-07-15
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Aug
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC |  | 2022-05-27 | 2022-06-03 | 2022-08-05 | 2022-08-12 | 2022-08-19 | 2022-08-26 | 2022-08-31
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [12 empty] | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2 format already fix start develop | next week start | DP PE almost finish | 1 line first in Aug next week start | 1 line start other Sep | next week other line Sep all finish
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03; 2022-08-12 to 2022-08-26
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [11 empty] | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination; 2022-08-05: test again need; 2022-08-12: test finish no reply next week push user; 2022-08-19: They use already
[6 empty] | Result |  |  |  |  | 1 | bar: 2022-08-12 to 2022-08-19
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-08-12: next Monday HR submit document; 2022-08-19: Analyse Result report to GM; 2022-08-26: make schedule Aug; 2022-08-31: Developing next week internal test
[6 empty] | Result |  |  |  | 1 | 1 | 1 | bar: 2022-08-12 to 2022-08-31
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | application install next week test | 1 time test ok 2nd time not ok PE data | OCS testing 18l PE not yet finish | PE OCS/18l finish need test | all finish
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03; 2022-08-12 to 2022-08-31
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-08-12: Sep; 2022-08-26: not yet receive; 2022-08-31: not yet receive
Result | bar: 2022-08-31
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | need discuss | hold meeting with PSCD | I try to make demo | Sep demo PSCD meeting next week | demo version make
[6 empty] | Result |  |  |  |  | 1 | bar: 2022-08-26 to 2022-08-31
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | next week meeting | kick off already make clear scope | scope making | next week scope after holiday review | study Phong san
[6 empty] | Result |  |  |  |  | 1 | bar: 2022-08-26
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [6 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 | 6
Result
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [6 empty] | 1 | 1 | 1 |  |  |  |  | 0.5 |  | 2022-05-27: DEV/INFRA
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 1728 |  |  | meeting already sample, scope, | scope nextweek I will check | develop start | developing finish next week test
Result | bar: 2022-08-12; 2022-08-31
DEV | 17 |  |  |  |  | Plan
Result
[7 empty] | 4 | 5 | 11 | 10 | 10 | 6 | 6 | 5 | 5 | 6 | 5 | 4
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
DEV TOTAL(RESULT)
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [17 empty] | finally no problem | finally no problem | finally no problem | finally no problem | finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [13 empty] | OK ne | Next Monday process checking | new flowchart after make clear check | Next week meeting but postpone after current project | pending
Result | bar: 2022-08-12 to 2022-08-31
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan
Result
DEV | 21 |  | seven eleven | Hien |  | Plan | [17 empty] | complete | complete | complete | complete | complete
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Sep
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-08-31 | 2022-09-16 | 2022-09-23
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | [12 empty] | 5.4 |  |  | Testing, Some revise | test so so OK format not match-> training | bar: Apr to Jun
[5 empty] | Binh | Result | bar: Apr to Jun
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | [14 empty] | 552 | Change from Box by box to model by model | testing with PIC | bar: Apr to Jun
Result | bar: Apr to Jun
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan | [15 empty] | 2 format already fix start develop | next week start | bar: May to Jul
[5 empty] | Tan | Result | bar: Jun to Jul
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan | [14 empty] | 240 | VB6 version now | Phong san | bar: Jun to Jul
Result | bar: Jun to Jul
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [15 empty] | for special destination | bar: Sep to Oct
Result | bar: Aug to Sep
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan | [17 empty] | Developing next week internal test | next week internal check fial week explain Iwamura san | next week make new cource and demo to Iwaura san | bar: Jun to Aug
Result | bar: Aug to Sep
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan | [15 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | all finish | bar: Jun to Aug
[5 empty] | Son | Result | bar: Jun to Jul
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan | [17 empty] | not yet receive | not yet | minimum version 27 Sep | bar: Aug to Nov
Result | bar: Oct
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan | [17 empty] | demo version make | next week internl discuss final week explain | next week explanation | bar: Jul to Mar
Result | bar: Aug to Sep
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan | [15 empty] | at first apply MEBD |  | study Phong san | internal meeting survey finish | local discussion scope need make clear next week planning | bar: Jul to Mar
Result | bar: Sep
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [13 empty] | 1 | 6 |  |  |  |  | Next month start project | bar: Oct to Jan
Result
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | bar: Jan to Mar
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [13 empty] | 0.5 |  | DEV/INFRA | bar: Oct to Dec
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [12 empty] | 1.5 | bar: Dec to Feb
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [13 empty] | 0.5 | bar: Jan to Mar
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan | [12 empty] | 1.7 |  | 1.5 | 1728 |  | developing finish next week test | Trial using no issue -> go live | finish next week go live | bar: Aug to Sep
[6 empty] | Result | [12 empty] | 2.3 |  | 576 | bar: Sep
DEV | 17 |  |  |  |  | Plan | [14 empty] | 2.304
Result
[7 empty] | 4 | 5 | 11 | 9 | 9 | 10 | 7 | 5 | 5 | 6 | 5 | 4
[7 empty] | Oct: DEV TOTAL(PLAN) | 8.6 | 2
[7 empty] | Oct: DEV TOTAL(RESULT) | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [17 empty] | finally no problem | finally no problem | finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan | [17 empty] | pending |  | Close | bar: Jul
Result
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [18 empty] | Next Monday | Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan | [17 empty] | complete | complete
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Oct
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | [12 empty] | 5.4 |  |  | Testing, Some revise | test so so OK format not match-> training | bar: Apr to Jun
[5 empty] | Binh | Result | bar: Apr to Jun
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | [14 empty] | 552 | Change from Box by box to model by model | testing with PIC | bar: Apr to Jun
Result | bar: Apr to Jun
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan | [15 empty] | 2 format already fix start develop | next week start | bar: May to Jul
[5 empty] | Tan | Result | bar: Jun to Jul
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan | [14 empty] | 240 | VB6 version now | Phong san | bar: Jun to Jul
Result | bar: Jun to Jul
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [15 empty] | for special destination | bar: Sep to Oct
Result | bar: Aug to Sep
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan | [17 empty] | next week make new cource and demo to Iwaura san | bar: Jun to Aug
Result | bar: Aug to Sep
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan | [15 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | bar: Jun to Aug
[5 empty] | Son | Result | bar: Jun to Jul
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan | [17 empty] | minimum version 27 Sep | 6 process Next week golive | bar: Aug to Nov
Result | bar: Oct
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan | [17 empty] | next week explanation | preparation new chart business flow making | bar: Jul to Mar
Result | bar: Aug to Sep
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan | [15 empty] | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | bar: Jul to Mar
Result | bar: Sep
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [13 empty] | 1 | 6 |  |  | Next month start project | scope finish in this month | bar: Oct to Jan
Result | bar: Oct
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | bar: Jan to Mar
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [13 empty] | 0.5 |  | DEV/INFRA |  |  | LAN preparation | bar: Oct to Dec
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [12 empty] | 1.5 | bar: Dec to Feb
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [13 empty] | 0.5 | bar: Jan to Mar
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan | [12 empty] | 1.7 |  | 1.5 | 1728 |  | finish next week go live | bar: Aug to Sep
[6 empty] | Result | [12 empty] | 2.3 |  | 576 | bar: Sep
DEV | 17 |  |  |  |  | Plan | [14 empty] | 2.304
Result
[7 empty] | 4 | 5 | 11 | 9 | 9 | 10 | 8 | 5 | 5 | 6 | 5 | 4
[7 empty] | Oct: DEV TOTAL(PLAN) | 8.6 | 2
[7 empty] | Oct: DEV TOTAL(RESULT) | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [17 empty] | finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan | [17 empty] | Close | bar: Jul
Result
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [17 empty] | Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan | [17 empty] | Close | bar: Jul
Result
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | bar: Dec
Result
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | bar: Nov to Dec
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Nov
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | [12 empty] | 5.4 |  |  | Testing, Some revise | test so so OK format not match-> training | bar: Apr to Jun
[5 empty] | Binh | Result | bar: Apr to Jun
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | [14 empty] | 552 | Change from Box by box to model by model | testing with PIC | bar: Apr to Jun
Result | bar: Apr to Jun
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan | [15 empty] | 2 format already fix start develop | next week start | bar: May to Jul
[5 empty] | Tan | Result | bar: Jun to Jul
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan | [14 empty] | 240 | VB6 version now | Phong san | bar: Jun to Jul
Result | bar: Jun to Jul
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [15 empty] | for special destination | bar: Sep to Oct
Result | bar: Aug to Sep
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan | [17 empty] | next week make new cource and demo to Iwaura san | bar: Jun to Aug
Result | bar: Aug to Sep
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan | [15 empty] | PE setup almost finish collecting data program(shipping process already using) | file format checking | bar: Jun to Aug
[5 empty] | Son | Result | bar: Jun to Jul
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan | [17 empty] | minimum version 27 Sep | 6 process Next week golive | trial | bar: Aug to Nov
Result | bar: Oct to Nov
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan | [17 empty] | next week explanation | preparation new chart business flow making | Move to PSDC, together make | bar: Jul to Mar
Result | bar: Sep to Nov
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan | [15 empty] | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | bar: Jul to Mar
Result | bar: Oct to Nov
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [13 empty] | 1 | 6 |  |  | Next month start project | scope finish in this month | Fix scope and inform change plan | bar: Nov to Mar
Result | bar: Nov to Dec
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | bar: Jan to Mar
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [13 empty] | 0.5 |  | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | bar: Nov to Dec
Result | bar: Nov
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [12 empty] | 1.5 | bar: Dec to Feb
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [13 empty] | 0.5 | bar: Jan to Mar
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan | [12 empty] | 1.7 |  | 1.5 | 1728 |  | finish next week go live | bar: Aug to Sep
[6 empty] | Result | [12 empty] | 2.3 |  | 576 | bar: Sep
DEV | 17 |  |  |  |  | Plan | [14 empty] | 2.304
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 10 | 6 | 6 | 6 | 5
[7 empty] | Oct: DEV TOTAL(PLAN) | 8.6 | 2
[7 empty] | Oct: DEV TOTAL(RESULT) | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [17 empty] | finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan | [17 empty] | Close | bar: Jul
Result | bar: Jul
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [17 empty] | Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan | [17 empty] | Close | bar: Jul
Result | bar: Jul
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | bar: Dec
Result
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | bar: Nov to Dec
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Dec
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-12
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [11 empty] | 552 | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2022-05-27: 2 format already fix start develop; 2022-06-03: next week start
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [10 empty] | 240 | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-09-23: next week make new cource and demo to Iwaura san
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-05-27: PE setup almost finish collecting data program(shipping process already using); 2022-06-03: file format checking
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-09-23: minimum version 27 Sep; 2022-10-14: 6 process Next week golive; 2022-12-05: trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 9 | All Depts | Total Visualize System Module: 1,2,3 | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | next week explanation | preparation new chart business flow making | Move to PSDC, together make | PSCD make sample 3 page
[6 empty] | Result | [5 empty] | 1 | 1 | 1
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | Combine function & waiting Prod prepair device for trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 6 |  |  | Next month start project | scope finish in this month | Fix scope and inform change plan | Doing
[6 empty] | Result | [7 empty] | 1 | 1
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1
Result
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [7 empty] | 1 | 1 |  |  |  |  | 0.5 |  | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | LAN decide, Dung san request Wifi => must decide this week
Result
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5 |  |  | 2022-10-14: Consider cancel. Focus into items: 11, 12, 15
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Dao | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728; 2022-09-23: finish next week go live
[6 empty] | Result | [5 empty] | 1 | [6 empty] | 2.3 |  | 576
DEV | 17 |  |  |  |  | Plan | [14 empty] | 2.304
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 9 | 6 | 6 | 6 | 5
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
[13 empty] | DEV TOTAL(RESULT) | [5 empty] | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [15 empty] | 2022-09-23: finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [15 empty] | 2022-09-23: Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | [8 empty] | 1 | [6 empty] | 2022-12-12: Prod request more. Modify function
Result
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | [7 empty] | 1 | 1 | 1 | [5 empty] | 2022-12-12: Setting 1 line and test OK. Inform to Prod request PE setup PC, network, Log file…
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider cancel. Focus to 11, 12, 15
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: consider select or not

## DEV_Jan
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-12 | 2023-06-01 | 13/01/2023 | 2023-03-02
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [11 empty] | 552 | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2022-05-27: 2 format already fix start develop; 2022-06-03: next week start
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [10 empty] | 240 | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-09-23: next week make new cource and demo to Iwaura san
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-05-27: PE setup almost finish collecting data program(shipping process already using); 2022-06-03: file format checking
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-09-23: minimum version 27 Sep; 2022-10-14: 6 process Next week golive; 2022-12-05: trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 9 | All Depts | Total Visualize System | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 2022-09-23: next week explanation; 2022-10-14: preparation new chart business flow making; 2022-12-05: Move to PSDC, together make; 2022-12-12: PSCD make sample 3 page | Kaizen collect data already
[6 empty] | Result | [5 empty] | 1 | 1 | 1 | 1
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | Combine function & waiting Prod prepair device for trial |  | Inform to MG & GM about schedule golive | Prod not yet answer plan
[6 empty] | Result | [6 empty] | 1 | 1 | 1
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 6 | 2022-09-23: Next month start project; 2022-10-14: scope finish in this month; 2022-12-05: Fix scope and inform change plan; 2022-12-12: Doing | Test 1 scheme Doing other type | Doing other type
[6 empty] | Result | [7 empty] | 1 | 1 | 1
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1 | [10 empty] | Meeting & disscus | Programing
[6 empty] | Result | [9 empty] | 1
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [7 empty] | 1 | 1 | 1 |  |  |  | 0.5 |  | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | LAN decide, Dung san request Wifi => must decide this week | Confirm Trinh san finished? | Trinh, Viet install FTP | Configuration service and function use OK.
[6 empty] | Result | [9 empty] | 1
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5 |  |  | 2022-10-14: Consider cancel. Focus into items: 11, 12, 15 | Move to March | Move to March
Result
DEV | 15 | SCM | Auto Verify customs declaration data | Phong | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5 | [9 empty] | Change method - Cancel
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728; 2022-09-23: finish next week go live
[6 empty] | Result | [5 empty] | 1 | [6 empty] | 2.3 |  | 576
DEV | 17 | All Depts | Traceability New Product | Hien Phong |  | Plan | [10 empty] | 1 | 1 |  |  | 2.304
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 9 | 8 | 10 | 7 | 6
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
[13 empty] | DEV TOTAL(RESULT) | [5 empty] | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [15 empty] | 2022-09-23: finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [15 empty] | 2022-09-23: Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | [8 empty] | 1 | [6 empty] | 2022-12-12: Prod request more. Modify function; 2023-06-01: go-live | go-live
Result
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | [7 empty] | 1 | 1 | 1 | [5 empty] | 2022-12-12: Setting 1 line and test OK. Inform to Prod request PE setup PC, network, Log file…; 2023-06-01: OK. Prod & PE Plan after change layout | OK. Prod & PE Plan after change layout
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider cancel. Focus to 11, 12, 15
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chane to new process, new method, direct input from SAP to ECUS using API. No need verify

## DEV_Feb
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-12 | 2023-06-01 | 13/01/2023 | 2023-03-02 | 13/02/2023
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [11 empty] | 552 | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2022-05-27: 2 format already fix start develop; 2022-06-03: next week start
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [10 empty] | 240 | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-09-23: next week make new cource and demo to Iwaura san
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-05-27: PE setup almost finish collecting data program(shipping process already using); 2022-06-03: file format checking
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-09-23: minimum version 27 Sep; 2022-10-14: 6 process Next week golive; 2022-12-05: trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 9 | All Depts | Total Visualize System | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 2022-09-23: next week explanation; 2022-10-14: preparation new chart business flow making; 2022-12-05: Move to PSDC, together make; 2022-12-12: PSCD make sample 3 page | Kaizen collect data already |  | Visualize finished. Meeting with others dept for next plan
[6 empty] | Result | [5 empty] | 1 | 1 | 1 | 1
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | Combine function & waiting Prod prepair device for trial |  | Inform to MG & GM about schedule golive | Prod not yet answer plan | Trial on MCW(already) DP setting
[6 empty] | Result | [6 empty] | 1 | 1 | 1
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 6 | 2022-09-23: Next month start project; 2022-10-14: scope finish in this month; 2022-12-05: Fix scope and inform change plan; 2022-12-12: Doing | Test 1 scheme Doing other type | Doing other type | Doing other type
[6 empty] | Result | [7 empty] | 1 | 1 | 1
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1 | [10 empty] | Meeting & disscus | Programing | Programing
[6 empty] | Result | [9 empty] | 1
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [7 empty] | 1 | 1 | 1 |  |  |  | 0.5 |  | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | LAN decide, Dung san request Wifi => must decide this week | Confirm Trinh san finished? | Trinh, Viet install FTP | Configuration service and function use OK. | Server and services completed. LAN waitting PMD setting. Plan Feb finished
[6 empty] | Result | [9 empty] | 1
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5 |  |  | 2022-10-14: Consider cancel. Focus into items: 11, 12, 15 | Move to March | Move to March | Survey
[6 empty] | Result | [10 empty] | 1
DEV | 15 | SCM | Auto Verify customs declaration data | Phong | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5 | [9 empty] | Change method - Cancel | Change method - Cancel
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728; 2022-09-23: finish next week go live
[6 empty] | Result | [5 empty] | 1 | [6 empty] | 2.3 |  | 576
DEV | 17 | All Depts | Traceability New Product | Hien Phong |  | Plan | [10 empty] | 1 | 1 |  |  | 2.304 | [9 empty] | Meeting, not yet have cencept
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 9 | 8 | 10 | 8 | 6
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
[13 empty] | DEV TOTAL(RESULT) | [5 empty] | 2.3
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [15 empty] | 2022-09-23: finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [15 empty] | 2022-09-23: Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | [8 empty] | 1 | [6 empty] | 2022-12-12: Prod request more. Modify function; 2023-06-01: go-live | go-live
Result
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | [7 empty] | 1 | 1 | 1 | [5 empty] | 2022-12-12: Setting 1 line and test OK. Inform to Prod request PE setup PC, network, Log file…; 2023-06-01: OK. Prod & PE Plan after change layout | OK. Prod & PE Plan after change layout
Result
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider cancel. Focus to 11, 12, 15
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chane to new process, new method, direct input from SAP to ECUS using API. No need verify

## DEV_Mar
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-12 | 2023-06-01 | 13/01/2023 | 2023-03-02 | 13/02/2023 | 2023-03-03
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | [9 empty] | 5.4 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [11 empty] | 576 | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | [9 empty] | 1.2 |  | 1152 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2022-05-27: 2 format already fix start develop; 2022-06-03: next week start
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [10 empty] | 240 | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1 | [8 empty] | 1.1 |  | 960
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-09-23: next week make new cource and demo to Iwaura san
[6 empty] | Result |  |  |  |  | 1 | 1 | [6 empty] | 29
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-05-27: PE setup almost finish collecting data program(shipping process already using); 2022-06-03: file format checking |  |  |  | 0.52368
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-09-23: minimum version 27 Sep; 2022-10-14: 6 process Next week golive; 2022-12-05: trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 9 | All Depts | Total Visualize System | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 2022-09-23: next week explanation; 2022-10-14: preparation new chart business flow making; 2022-12-05: Move to PSDC, together make; 2022-12-12: PSCD make sample 3 page | Kaizen collect data already |  | Visualize finished. Meeting with others dept for next plan | collect more from AGM
[6 empty] | Result | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | Combine function & waiting Prod prepair device for trial |  | Inform to MG & GM about schedule golive | Prod not yet answer plan | Trial on MCW(already) DP setting | Trial on MCW(already) DP setting
[6 empty] | Result | [6 empty] | 1 | 1 | 1 | 1 | 1 |  | 4.72 |  | 130800
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 6 | 2022-09-23: Next month start project; 2022-10-14: scope finish in this month; 2022-12-05: Fix scope and inform change plan; 2022-12-12: Doing | Test 1 scheme Doing other type | Doing other type | Doing other type | Doing other type
[6 empty] | Result | [7 empty] | 1 | 1 | 1 | 1 |  |  | 1
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1 | [10 empty] | Meeting & disscus | Programing | Programing | Delay for PIC resign
[6 empty] | Result | [9 empty] | 1 | 1
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [7 empty] | 1 | 1 | 1 |  |  |  | 0.5 | 144 | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | LAN decide, Dung san request Wifi => must decide this week | Confirm Trinh san finished? | Trinh, Viet install FTP | Configuration service and function use OK. | Server and services completed. LAN waitting PMD setting. Plan Feb finished | Completed. Dept want to add more. => denied
[6 empty] | Result | [9 empty] | 1 |  |  | 0.4 |  | 0.288
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5 |  | 42 | 2022-10-14: Consider cancel. Focus into items: 11, 12, 15 | Move to March | Move to March | Survey | Programming DIP, Test DP, MCW
[6 empty] | Result | [10 empty] | 1 |  | 6 |  | 2.016
DEV | 15 | SCM | Auto Verify customs declaration data | Phong | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5 | [9 empty] | Change method - Cancel | Change method - Cancel
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728; 2022-09-23: finish next week go live
[6 empty] | Result | [5 empty] | 1 | [6 empty] | 2.3 |  | 576
DEV | 17 | All Depts | Traceability New Product | Hien Phong |  | Plan | [10 empty] | 1 | 1 |  |  | 2.304 | [9 empty] | Meeting, not yet have cencept | Meeting, not yet have cencept
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 9 | 8 | 12 | 12 | 6
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 8.6 | 2
[13 empty] | DEV TOTAL(RESULT) | [5 empty] | 50.12 | 1
DEV | 18 |  | Weight Check no detect shipment log file(DP) |  |  | Plan | [15 empty] | 2022-09-23: finally no problem
Result
DEV | 19 |  | e-invoice for issue in/out | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 20 |  | e-invoice for transportation note | Hien |  | Plan | [15 empty] | 2022-09-23: Close
Result
DEV | 21 |  | seven eleven | Hien |  | Plan |  |  |  | 1 | [11 empty] | 2022-09-23: Close
[6 empty] | Result |  |  |  | 1
DEV | 22 |  | Pallet ID verify and adding process | Hien |  | Plan | [8 empty] | 1 | [6 empty] | 2022-12-12: Prod request more. Modify function; 2023-06-01: go-live | go-live |  |  | Done
[6 empty] | Result | [8 empty] | 1
DEV | 23 |  | DECT weight Check outer carton | Minh |  | Plan | [7 empty] | 1 | 1 | 1 | [5 empty] | 2022-12-12: Setting 1 line and test OK. Inform to Prod request PE setup PC, network, Log file…; 2023-06-01: OK. Prod & PE Plan after change layout | OK. Prod & PE Plan after change layout |  |  | Done
[6 empty] | Result | [7 empty] | 1 | 1 | 1
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on Y28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider cancel. Focus to 11, 12, 15
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chane to new process, new method, direct input from SAP to ECUS using API. No need verify