## Summary
ISD FY2023 Projects Summary
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
COST DOWN | Plan | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 5
| Amount (K$/Y) | 1.4 | 8.7 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 34.1
| Actual | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 6
| Amount (K$/Y) | 5.87 | 0.7 | 10.9 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 41.47
QUAILITY/ POLICY/ MANAGEMENT | Plan | 4 | 2 | 3 | 0 | 2 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 17
| Actual | 2 | 2 | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 11
ISG FY2018 Cost Down Achievement Result
Item |  | Apr: Amount (K$/Y); Total: Result
Project |  | Apr: #REF!; Total: ¡
Other Activity |  | Apr: 16.3; Total: ¡
Total |  | Apr: #REF!; Total: ¡
SUM
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
CD | Original Plan | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Result- actual (update 22Jun) | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy/quanlity | Original Plan | 4 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Result - actual (update 22Jun) | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
In Progress
O
Achieved
Non - Achieved
X
MONTH
ITEMS

## FY23(SAP)_
No | Main item | HC | Section | Progress | Target | Status | Plan/ Result | Date | Merit (K$) | HC | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | 2023-04-27 | PIC ISD | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-29 | 2023-10-31 | 2023-11-30 | 2023-12-28
1 | SAP- suggest Sale based on inventory |  |  | 100 |  | Done [But Delay] | Original Plan | 2023-04-01 | Policy |  | 1 | [11 empty] | Finish: PSCD using But Shortage material still need to upload | Lam | Finished
Adjusted Plan
[7 empty] | Acrtual Result | 2023-05-01 | Policy |  | 1 | 1
2 | Shipping Advice (v3) |  | PUS | 100 |  | Done | Original Plan | 2023-05-01 | 8 |  | 1 | 1 | [10 empty] | Already transfer V1P and Dept using to compare data | Trung | Finish (supporting for some special issue)
Adjusted Plan
[7 empty] | Acrtual Result | 2023-04-01 | 5.7 |  | 1
3 | Extend function Auto convert BOM PAPVN/BCBU/SCBU/MEBD (MWO already FY20) |  | PMS | 100 |  | Done | Original Plan | 2023-04-01 | 1.4 |  | 1 | [11 empty] | Finish | Trung | Finished
Adjusted Plan
[7 empty] | Acrtual Result | 2023-04-01 | 0 |  | 1
4 | Convert tool (BOM, Master)-New Product |  | FE | 100 |  | Done [But Delay] | Original Plan | 2023-05-01 | Quality |  | 1 | 1 | [10 empty] | 1. Studying (finish ) 2. Making FS and B&A | Trung | 1. Studying (finished) 2. Making FS and B&A (finished) 3. Developping | 4. Finished
[7 empty] | Adjusted Plan | 2023-07-01 |  |  |  | 1 | 1 | 1
[7 empty] | Acrtual Result | 2023-06-23 |  |  | 1 | 1 | 1
5 | Support new Product TV |  | ALL | 100 |  | Done | Original Plan | 2023-04-23 | Quality |  | 1 | 1 | [11 empty] | Hoa
Adjusted Plan
[7 empty] | Acrtual Result | 2023-04-23 |  |  | 1
6 | EDI data with special supplier (PPHK, GPGC) IPS format |  |  | 100 |  | Done | Original Plan | 2023-04-23 | Policy |  | 1 | 1 | [10 empty] | 1. supporting to register SCM navi VV01 (finished) | Thuy, Hoa | 1. New TCM setting up for Invoice sending (finished) 2. IPS format studying (doing) | 3. Register new TCM for IPS format | Pending | IPS format: Submit TCM application form (finished 23Aug) |  |  | - Testing finished - Waiting Golive | - Testing finished - Waiting Golive
[7 empty] | Adjusted Plan | 2023-11-01 | [7 empty] | 1 | 1 | 1
[7 empty] | Acrtual Result | 2023-11-01 | [7 empty] | 1 | 1 | 1
7 | CMS data, G.UNI, ICAST |  |  | 75 |  | OnSC | Original Plan | 2023-08-01 | Policy |  |  | 1 | 1 | 1 | 1 | [7 empty] | 1. ICAST: Study BGJ again & register HULFT ID | Thuy | 1. G-UNI background Job setting (finished) 2. ICAST: HULFT registed 3. CMS data setting: T00021955 (doing) | 3. CMS data setting: T00021955 (finished) 4. ICAST: sending data | Finished |  |  |  | - G-UNI testing Host info changing (Finished) - SCBU start for CMS transmit (Finished)
[7 empty] | Adjusted Plan | 2023-12-01 | [5 empty] | 1 | 1 | 1 | 1 | 1
[7 empty] | Acrtual Result | [6 empty] | 1 | 1 | 1 | 1 | 1
8 | SAP HANA Planning(Pre-Project)-Blueprint Project- Realization- Test & training - Golive |  | ALL | 25 |  | OnSC | Original Plan | 2024-03-01 | Policy |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | ALL |  |  | 1. Prepare sanction for PSNV High Level Assessment | 1. Sanction for PSNV High Level Assessment (finished) 2. prepare High Level Assessment PSNV & PISCAP & Vendor (Sep23) | 2. prepare High Level Assessment PSNV & PISCAP & Vendor (Sep23) | Clarify, Discus and Decision for Key Changes for PP, MM, FICO, SD, QM
[7 empty] | Adjusted Plan | - | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | Acrtual Result | [7 empty] | 1 | 1 | 1 | 1
| Explain document (Flow, Approve) |  |  | 50 |  | OnSC hay Delay? | Original Plan |  |  |  | 1
Adjusted Plan
Acrtual Result
| FS-HANA |  |  | 50 |  | OnSC hay Delay? | Original Plan |  |  |  | 1 | 1 | [20 empty] | Oct~Dec/22
Adjusted Plan
Acrtual Result
| Explaination to Vendor (Deloite)-HANA |  |  | 50 |  | OnSC hay Delay? | Original Plan |  |  |  |  | 1 | 1
Adjusted Plan
Acrtual Result
| Workshops SAP team-PISCAP-Deloite |  |  | 50 |  | OnSC hay Delay? | Original Plan |  |  |  |  | 1 | 1 | 1 | 1
Adjusted Plan
Acrtual Result
| Summary-HANA |  |  | 50 |  | OnSC hay Delay? | Original Plan | [7 empty] | 1
Adjusted Plan
Acrtual Result
| Final summary Report and Proposal |  |  | 50 |  | OnSC hay Delay? | Original Plan | [7 empty] | 1 | 1
Adjusted Plan
Acrtual Result
| Review, study & Implementation HANA |  |  | 50 |  | OnSC hay Delay? | Original Plan | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1
Adjusted Plan
Acrtual Result
9 | SOX |  | ALL | 100 |  | Done | Original Plan | 2023-08-01 | Quality |  |  |  |  | 1 | 1 | [8 empty] | ALL |  |  | 1. Doing ITAC & ITGC | ITAC & ITGC : submit & review (Aug23)
[7 empty] | Adjusted Plan | -
[7 empty] | Acrtual Result | 2023-07-23 | [5 empty] | 1 | 1
10 | Addition currency JPY |  |  | 100 |  | Done | Original Plan | 2023-06-01 | Policy |  | 1 | 1 | 1 | [9 empty] | 1. Testing basic case : 1 issue 2. Collected request from Procurement & Acc (finished) | ALL | 1. Request Japan to adjust function (4 Tcode) | 2. Setup new vendor (JPY) 3. EDI testing (Same Gcode) | 2. New vendor with currency JPY (finsihed) 3. EDI transmitted OK 4. Info record master decimal 3 5. Back JPY currency from 3 --> 0 | Issued and EDI PO Finished (Aug23)
[7 empty] | Adjusted Plan | 2023-08-01
[7 empty] | Acrtual Result |  |  |  | 1 | 1 | 1
11 | Send data SAP --> Ecus |  |  | 100 |  | Done | Original Plan | 2023-10-01 | 24 |  |  |  |  | 1 | 1 | 1 | 1 | [6 empty] | Trung,Lam |  | 1. Making scope | 1. Scope (finished) 2. Demo interface (finished) 3. Upload Material master (Finished) 4. Collect & Cretate Ad-on table (Finished) 5. Upgrade API testing from Thai Son 6. Get data (outside SAP) : doing | 6. Get data (outside SAP) : finished 7. System Integration Test: - Import: 50% completed (test case (50/100) - Export: 60% completed (test case (60/100) | 7. System Integration Test: - Import: 70% completed (test case (70/100) - Export: 80% completed (test case (80/100) | Finsihed (Oct-23)
Adjusted Plan
[7 empty] | Acrtual Result | 2023-10-30 | [5 empty] | 1 | 1 | 1 | 1
12 | Receive data Ecus --> SAP |  |  | 100 |  | Done | Original Plan | 2023-11-01 | [8 empty] | 1 | 1 | [5 empty] | Trung,Lam | [6 empty] | Finsihed (Nov-28). - Support after Golive - Consider for Special case
Adjusted Plan
[7 empty] | Acrtual Result | 2023-11-28 | [8 empty] | 1 | 1
13 | Speial case Issue Ecus & SAP |  |  | 100 |  | Done | Original Plan | 2024-02-24 | Quality | [9 empty] | 1 | 1 | 1 |  |  | Trung | [6 empty] | Finsihed (Nov-28). - Support after Golive - Consider for Special case
Adjusted Plan
[7 empty] | Acrtual Result | [11 empty] | 1
14 | Apply "Auto Sub material" for PMD |  |  | 100 |  | Done | Original Plan | 2024-01-24 | Quality | [9 empty] | 1 | 1 |  |  |  | Lam | [6 empty] | Finsihed (Nov-28). - Support after Golive - Consider for Special case
Adjusted Plan
Acrtual Result
15 | New report for Sub (Procurement) |  |  | 100 |  | Done | Original Plan | 2024-03-24 | Quality | [11 empty] | 1 | 1 |  | Lam | [6 empty] | Finsihed (Nov-28). - Support after Golive - Consider for Special case
Adjusted Plan
Acrtual Result
| Other | [5 empty] | Original Plan | [12 empty] | 1 | 1 | 1 | 1. RO issue : Delivery date not update 2. Sub material function improvement | Hoa, Thuy | 2. Sub material function improvement (doing) 3. EDI Invoice error | 2. Sub material function improvement (finished) 3. Testing "Exchange rate currency" new Currency type (testing) | 1. Blue Yonder : studying document 2. New EDI transmision SCBU | 1. Blue Yonder : studying document 2. Japan shipment (New-Mochikaeri) 00021631 PEAC-SCBU: EDI testing 28-Aug – 15-Sep 3. New Plant setting up : Sep23 ~Oct23: requesting Japan for setting Plant code and Purchasing Oganization | 2. Japan shipment (New-Mochikaeri) 00021631 PEAC-SCBU: EDI testing (28-Aug – 15-Sep) : finsihed 3. New Plant setting up : Sep23 ~Oct23: - requesting Japan for setting Plant code and Purchasing Oganization (Finished) - Customize new Plant in SAP | 3. New Plant setting up: - UAT (finished) - Golive | - Support Tivi finish goods return on SAP - Apply "Auto Sub material" for PSCD & PMD - Studying "Sub contract process" on SAP - Setup New BGJ for Forecast transmit | - Studying "Sub contract process" on SAP - Add new GL account for ACD - Collecting items for BP24
Adjusted Plan
Acrtual Result
TOTAL MERIT SUMMARY | [6 empty] | Original Plan |  | 33.4
[7 empty] | Acrtual Result |  | 5.7
[7 empty] | Diff Amount |  | -27.7
Phut*0.023*12 = tien
|  |  | CD $ | plan: |  |  | #REF! | apr |  | 83h/y;1h=2$ | 0.166
[7 empty] | #REF! | may |  |  |  |  | 156h
|  |  |  | result |  |  | #REF! | apr |  | gio*2$*12 |  |  | 2583.36
[7 empty] | 0.7 | may |  | 8016 |  |  | 2.5834

## FY23(Develop)
No | Main item | Section | Dept. | Progress | Target | Status | Plan/ Result | Date | CD (K$) | HC | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | PIC ISD | 2023-05-31 | 2023-06-30 | 2023-07-27 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-29
1 | Traceability OLED TV: MCS, SMT: Master setting, DB create, add store procedure, function add | MCS/SMT/Others | Manufacturing | 100 |  | Done | Original Plan | 2023-05-01 | Management |  | 1 | 1 | [10 empty] | Minh/Phong | Compeled
[7 empty] | Plan |  |  |  | 1 | 1
[7 empty] | Result | 2023-05-01 |  |  | 1 | 1
2 | Traceability OLED TV: FA: Part control & verify, Weight check Pallet ID | FA | Manufacturing | 100 |  | Done | Original Plan | 2023-06-01 | Management |  | 1 | 1 | 1 | [9 empty] | Phong/Minh | 4 Process on FA line completed, Weight check 1st version, Pallet ID testing | Allmost completed Demura waiting PE confirm format Plan 10.Jul go-live | Completed
[7 empty] | Plan |  |  |  | 1 | 1 | 1
[7 empty] | Result | 2023-06-01 | 10.9 | 1 | 1 | 1 | 1
3 | Traceability OLED TV: PSCD: Shiment link: Jupiter warehouse shippment control & verify data, linkage JPT to PSNV | PSCD | PSCD | 100 |  | Done | Original Plan | 2023-06-01 | Management |  |  |  | 1 | [9 empty] | Hien | Meeting | Trial. Plan 10.Jul go-live | Completed
[7 empty] | Plan | [5 empty] | 1
[7 empty] | Result | 2023-06-01 |  |  |  |  | 1
4 | Android programing language training +1st month: basic structure +2nd month: practice and new develop +3rd month: focus mainly function +4th month: upgrade skill and review | Develop | ISD | 100 |  | Done | Original Plan | 2023-08-01 |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | Hien | - Structure of new programming finished - UI, layout, basic control, API web, API Mobile | - Practice - 1st exam | Developing base on actual project & review Kitting - Minh & GR-Phong | Basic training completed. Upgrade andvance skill in the future | Training for Tuan Anh
[7 empty] | Plan |  |  |  | 1 | 1 | 1 | 1 | 1
[7 empty] | Result | 2023-08-01 |  |  | 1 | 1 | 1 | 1 | 1
5 | FOSS upgrade following compliance - Android version Detail indicate on others document | MCS/FA | Proc | 67 |  | OnSC | Original Plan | 2024-04-01 | Management |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Minh/Phong |  | Document GR, Kitting making | GR: Auto, normal: develop finish, waitting test GR: 1by1 developing Kitting: FA develop finish, waitting test Checking: FA developing | GR local finished. Kitting FA finished Waitting New PDA for trial Kitting DIP start from Sept Re-search GR oversear - mobile printer | 1- GR local, oversea finished. Trial 1 device OK. Wait new device delivery and sample 5pcs trial 2- Kitting DIP, FA develop finished Now testing on 1 device trial with user | Finished testing on 1 device Next testing on 5 devicces of each process Continues develop kitting, supply | Test and trial on 5-10 devices. Middle of Dec, collect test result | finish develop checking, supply Fix bug some function Test all new device at GR
[7 empty] | Plan | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | Result | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Traceability Microwave change QR Code structure magnetron - Add production date & verification | FA/IQC | Manufacturing | 100 |  | Done | Original Plan | 2023-04-01 | Management |  | 1 | [11 empty] | Phong | Finished and golive
[7 empty] | Plan |  |  |  | 1
[7 empty] | Result | 2023-04-01 |  |  | 1
7 | Traceability Microwave change QR Code structure magnetron - Clear stock old part | FA/IQC | Manufacturing | 100 |  | Done | Original Plan | 2023-05-01 | 0.7 |  |  | 1 | [10 empty] | Phong | Finished and golive
[7 empty] | Plan |  |  |  |  | 1
[7 empty] | Result | 2023-05-01 | 0.7 |  |  | 1
8 | Outsourcing software Linkage & handover WMS SCM, IoT SMT, Free location SMT | SCM/SMT | Manufacturing | 60 |  | OnSC | Original Plan | 2024-03-01 | Management | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Dev |  |  |  |  | WMS server replicate Support installation HA test | SMT Free location receive document & explaination | KLEC sent document Hung Dao not yet | Meeting again ưith Hung Dao They delay to send document
[7 empty] | Plan | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | Result | [8 empty] | 1 | 1 | 1 | 1
9 | Create Debit Note new curency JP-YEN | ACD | ACD | 100 |  | Done | Original Plan | 2023-06-01 | Management |  |  |  | 1 | [9 empty] | Phong | Meeting | Trial. Go-live 19.Jun | Completed
[7 empty] | Plan | [5 empty] | 1
[7 empty] | Result | 2023-06-01 |  |  |  |  | 1
10 | FOSS balance stock and lot tool | MCS |  | 100 |  | Done | Original Plan | 2023-08-01 | [6 empty] | 1 | [7 empty] | T.Anh |  |  |  | Completed
[7 empty] | Plan | [7 empty] | 1
[7 empty] | Result | [7 empty] | 1
11 | Smart Warehouse Management System (Survey, make detail plan, calculate ROI, Fix Scope) | MCS |  | 100 |  | Done | Original Plan | [7 empty] | 1 | 1 | [6 empty] | Hien |  |  |  | GR: fixed Storage, kitting: review, waiting MCS, PUS send draf and process | Finish. Next make detail plan
[7 empty] | Plan | [7 empty] | 1 | 1
[7 empty] | Result | [7 empty] | 1 | 1
12 | Smart Warehouse Management System | Proc |  | 34 |  |  | Original Plan |  |  | 15 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | Hien | [5 empty] | training members, meeting with related dept, confirm process and fix scope of GR | Document and process finished SRS doc, UI confirm Start to develop API and logic mobile | Screens logic coding Tool create for supllier no-barcode case Website master, upload coding Make plan for SIT and UAT
[7 empty] | Plan | [9 empty] | 1 | 1 | 1
Result
13 | DP SECOM OEM model | FA |  | 100 |  | Done | Original Plan | 2023-11-01 | [8 empty] | 1 | 1 |  |  |  |  | Dev | [5 empty] | Confirm QP, product structure, process, start to develop: weight check, verify | Finished
[7 empty] | Plan | [9 empty] | 1 | 1
[7 empty] | Result | 2023-11-01 | [8 empty] | 1 | 1
DEVELOP TOTAL(PLAN)
DEVELOP TOTAL(RESULT)
Note on C6: Nguyen Van Hien: 1 project (tách theo 3 phòng) - 1 B&A. khi nào hoàn thành all thì mới đưa vào báo cáo. Total: HC: 1 CD: 10.9 ROI: 0.2
Note on L8: Nguyen Van Hien: 1 OP x 600$/Year
Note on C30: Add new Quick support only
Note on C33: Add
Note on C36: Add

## FY23(BPI)
Progress
No | Main item | CD (K$) | HC | section | Dept. | Progress | Target | Status | Plan/ Result | Date | CD (K$) | HC | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | 2023-04-27 | PIC ISD | 2023-05-31
1 | Inventory analysis | Quality |  | PUS |  | 100 |  | Done [But Delay] | Original Plan | 2023-05-21 | Quality |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | Finish: PSCD using But Shortage material still need to upload | Toan, Hoa
[9 empty] | Plan | 2023-12-31
[9 empty] | Result | 2023-11-19 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Control scrap | Quality |  | PUS |  | 100 |  | Done | Original Plan | 2023-09-01 | Quality | [5 empty] | 1 | 1 | [6 empty] | Already transfer V1P and Dept using to compare data | Toan, Hoa
[9 empty] | Plan | 2023-09-30
[9 empty] | Result | 2023-09-30 | [6 empty] | 1 | 1
3 | Check NG part return maker |  |  | PUS |  | 25 |  | OnSC | Original Plan | 2023-10-01 | Quality | [7 empty] | 1 | 1 |  |  |  |  | Finish | Toan
[9 empty] | Plan | 2023-12-04 | [10 empty] | 1 | 1
Result
4 | Sale Deadstock |  |  | PUS |  | 20 |  | OnSC | Original Plan | 2023-12-01 | Quality | [9 empty] | 1 |  |  |  | 1. Studying (finish ) 2. Making FS and B&A | Hoa
Plan
Result
Original Plan
Plan
Result
[9 empty] | Original Plan | [15 empty] | 1. supporting to register SCM navi VV01 (finished)
Plan
Result
[9 empty] | Original Plan | [15 empty] | 1. ICAST: Study BGJ again & register HULFT ID
Plan
Result
Original Plan
Plan
Result
Original Plan
Plan
Result
[9 empty] | Original Plan | [18 empty] | Oct~Dec/22
Plan
Result
Original Plan
Plan
Result
Original Plan
Plan
Result
Original Plan
Plan
Result
Original Plan
Plan
Result
Original Plan
Plan
Result
9 | [8 empty] | Original Plan
Plan
Result
10 | [8 empty] | Original Plan | [15 empty] | 1. Testing basic case : 1 issue 2. Collected request from Procurement & Acc (finished)
Plan
Result
[9 empty] | Original Plan | [15 empty] | 1. RO issue : Delivery date not update 2. Sub material function improvement
Plan
Result
Original Plan
Plan
Result
| SAP TOTAL(PLAN) | 0 | 0
| SAP TOTAL(RESULT) | 0 | 0

## count 22Jun
|  | SAP | [11 empty] | Dev | [11 empty] | BP | [11 empty] | SUM
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
CD | Original Plan | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 5
| Result (update 22/Jun) | SAP Apr: 2; SAP May: 0; Dev Apr: 0; Dev May: 1; BP Apr: 0; BP May: 0; SUM Apr: 2; SUM May: 1; SUM Jun: 0; SUM Jul: 0; SUM Aug: 0; SUM Sep: 0; SUM Oct: 0; SUM Nov: 0; SUM Dec: 0; SUM Jan: 0; SUM Feb: 0; SUM Mar: 0 | 3
Policy/quanlity | Original Plan | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 2 | 3 | 0 | 3 | 0 |  | 1 | 0 | 1 | 0 | 2 | 16
| Result (update 22/Jun) | SAP Apr: 1; SAP May: 1; Dev Apr: 1; Dev May: 1; BP Apr: 0; BP May: 0; SUM Apr: 2; SUM May: 2; SUM Jun: 0; SUM Jul: 0; SUM Aug: 0; SUM Sep: 0; SUM Oct: 0; SUM Nov: 0; SUM Dec: 0; SUM Jan: 0; SUM Feb: 0; SUM Mar: 0 | 4

## Dev-Unplan
| FY2023 IT DEVELOPMENT SUMMARY PROJECTS | [16 empty] | 3
[8 empty] | 20.9 | 426.3961 | 99.339 | [5 empty] | 125.4 |  | 304.5
RANK | No | Dept | Section | No by dep. | Items | Purpose | Project Type | Merit |  | Invest KUSD | Estimate ROI | Section PIC | IT PIC | IT Develop (month) | IT Develop (pax) | IT Dev Fee K$ | ROI | Outsourcing Fee K$ | ROI Outsourcing | IT Evaluation | Kind | Remarks
[8 empty] | Man | CD (KUSD)
| 1 | Prod | ALL | M-1 | Expand IoT system from SMT to DIP-FCT-FA WIP, production plan/ result, quality, checksheet less, material verify | Man reduce Management improvement | HC | 4 | 24 | 70 | 2.9167 | Hai Kien Khanh | Hien | 5 | 3 | 18 | 3.6667 | 45 | 4.7917 | Consider | Outsourcing | Reduce function as disscus before 3 version: 1st 200k, 2rd: 100k, 3nd: 60K
| 2 | Prod | SMT | M-2 | Fix Bugs for IoT systems Hour progress, shift calendar, Quality defect, WIP BF/TF | PRDCV project No warranty, noback up server, upgrade need fee | Quality | 0 | 0 | 0 | 0 | Trung | Hien | [5 empty] | #DIV/0! | Consider | Outsourcing | Can not touch
| 3 | Prod | SMT | M-3 | Expand (add more function) for IoT systems Dashboard, target line, slowmoving, WIP, indication, ECN | PRDCV project No warranty, noback up server, upgrade need fee | Management | 0 | 0 | 0 | 0 | Trung | Hien | [5 empty] | #DIV/0! | Consider | Outsourcing | Can not touch
| 4 | Prod | SMT | M-4 | Optimize make plan for SMT to reduce leadtime 1day project | Joy schedule & Excel tool | Management | 0 | 240 | 0 | 0 | Trung | Hien | [5 empty] | 0 | Consider | Japan | Confirm to Japan
| 5 | Prod | ALL | M-6 | Auto B/F from FCT to FA, SCS | Management improvement | Management | 1 | 6 | 0 | 0 | Tho | Hien | 1 | 1 | 1.2 | 0.2 | 3 | 0.5 | Consider | In-house
| 6 | Prod | DP | M-7 | Improve weight check: auto select item "modelshiping" | Management improvement | Management | 0 | 0 | 0 | 0 | Trung | Hien | 1 | 1 | 1.2 | #DIV/0! | 3 | #DIV/0! | No need | In-house | 5 version: Double ID, Malaysia, 6 digits, dummy serial, shipping
| 7 | Prod | ALL | M-8 | Make software link data control manual book, leaflet, children model..to weitgh check to prevent human mistake | Quality management | Quality | 0 | 0 | 0 | 0 | Doan | Hien | 2 | 1 | 2.4 | #DIV/0! | 6 | #DIV/0! | Consider | In-house
| 8 | Prod | MCW | M-9 | Change program printing label: input date/month/year auto | Quality management | Quality | 0 | 0 | 0 | 0 | Nhien | Hien | [5 empty] | #DIV/0! | No need | In-house | Request Change design by Japan. No need
| 9 | Prod | PJ | M-10 | Add Traceability system for accessories 2: Link from accessories 2 to weight check | Quality management | Quality | 0 | 0 | 0 | 0 | Quyen | Hien | 0.5 | 1 | 0.6 | #DIV/0! | 1.5 | #DIV/0! | Consider | In-house
| 10 | Prod | PJ | M-11 | Modify Traceability system of appearance process: Delete item: Check Again at this process | Quality management | Quality | 0 | 0 | 0 | 0 | Quyen | Hien | 0.5 | 1 | 0.6 | #DIV/0! | 1.5 | #DIV/0! | Consider | In-house
| 11 | Prod | PJ | M-12 | Improvement Traceability system of Optical process: add more item reset data Traceability for repair set | Quality management | Quality | 0 | 0 | 0 | 0 | Quyen | Hien | 0.5 | 1 | 0.6 | #DIV/0! | 1.5 | #DIV/0! | Consider | In-house
| 12 | Prod | DP | M-13 | Link serial no from weight check to inspection report | Quality management | Quality | 0 | 0 | 0 | 0 | Doan | Hien | [5 empty] | #DIV/0! | Ignore | In-house | already discussed with PIC
| 13 | Prod | ALL | M-5 M-14 | Install MCS portal to inform MCS pull in/back supply material timely | Quality management | Quality | 0 | 0 | 0 | 0 | Lieu | Hien | [5 empty] | #DIV/0! | Ignore | In-house | already discussed with PIC (combine No M-5,M-14, Communicate software)
| 14 | QCD | ALL | Q-1 | Link weight check system from FA --> OQC --> Shipment | Quality management | CD/HC | 2 | 12 | 0 |  | Ha | Hien | 3.5 | 1 | 4.2 | 0.35 | 10.5 | 0.875 | Consider | In-house | Reduce 2 HC?
| 15 | QCD | MCW | Q-2 | CPK analyze | Quality management | Management | 0.5 | 0 | 0 | 0 | Ha | Hien | 2 | 1 | 2.4 | #DIV/0! |  | #DIV/0! | Ignore | In-house | Not clear method
| 16 | QCD | ALL | Q-3 | 4M information system | Quality management | Management | 0.5 | 6.6501 | 0.939 | 0 | Thanh | Hien | 2 | 1 | 2.4 | 0.5021 | 6 | 1.0434 | Consider | In-house
| 17 | QCD | ALL | Q-4 | All Defect control by Server | Quality management | Quality | 0.5 | 5.7 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 18 | QCD | ALL | Q-5 | Request more completed and perfect Free location | Quality management | Quality | 0.1 | 0.72 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 19 | QCD | ALL | Q-6 | RoHS inspection Print part card | Quality management | Quality | 0.2 | 1.2 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 20 | QCD | ALL | Q-7 | Not inspection | Quality management | Quality | 0.1 | 0.6 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 21 | QCD | ALL | Q-8 | Need completed and improve for Free location Project for IQC | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 22 | QCD | ALL | Q-9 | Select Ok / NG | Quality management | Quality |  |  | 0 |  | Tho | Hien | [5 empty] | #DIV/0! | No need | In-house | Already, No need
| 23 | QCD | ALL | Q-10 | Upload user | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | No clear function
| 24 | QCD | ALL | Q-11 | Upload Master Reability & WI | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 25 | QCD | ALL | Q-12 | Check-sheet system | Quality management | Quality | 0.2 | 1.2 | 0 |  | Tho | Hien | [5 empty] | 0 | No need | In-house | Already, No need
| 26 | QCD | ALL | Q-13 | Filter Received Date, category | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | No clear function
| 27 | QCD | ALL | Q-14 | Delete checking | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | No clear function
| 28 | QCD | ALL | Q-15 | Wating Inspection RoHS | Quality management | Quality | 0.1 | 0.36 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | New request, not yet explain, no clear merit
| 29 | QCD | ALL | Q-16 | Wating Inspection RoHS | Quality management | Quality | 0.2 | 1.4 | 0 |  | Tho | Hien | [5 empty] | 0 | Consider | In-house | No clear function
| 30 | HR | ALL | H-1 | E-leave control | Quality management | Management | 0 | 22.966 | 0 |  | Hoa | Hien | 4 | 1 | 4.8 | 0.209 | 12 | 0.52251 | Consider | In-house
| 31 | GA | ALL | G-1 | Stationery control | Quality management | Management | 0 | 1.88 | 0 |  | Hang | Hien | 2 | 1 | 2.4 | 1.2766 | 6 | 3.1915 | Consider | In-house
| 32 | PROC | MCS | Proc-17 | Auto Print receive card for local material by mobile printer(DA) | Quality management | Management | 0 | 0 | 0 |  | Hoang | Hien | 1.5 | 1 | 1.8 | #DIV/0! | 4.5 | #DIV/0! | Ignore | In-house | No clear merit
| 33 | PROC | MCS | Proc-18 | Auto back flush and receiving card PMD/Rainbow | Quality management | Management | 0 | 11.52 | 0 |  | Hoang | Hien | 2 | 1 | 2.4 | 0.20833 | 6 | 0.52083 | Consider | In-house | Not clear all process
A | 34 | PROC | MCS | Proc-19 | Free location and E-Inventory card - Auto print Stock Card, GR local, oversea - Storage, freelocation, Kitting, kitting outside - E-stock card, E-inventory | Quality management | HC | 9 | 46.08 | 16.4 | 0.3559 | Hoang | Hien | 10 | 5 | 60 | 1.658 | 150 | 3.6111 | Consider | In-house/ Outsourcing | Not jump process. Follow system process: GR-> Freelocation-> Insp -> Storage-> Kitting -> Check kitting -> Supply
| 35 | PROC | MCS | Proc-20 | Update layout for E-map Free location at receiving area | Quality management | Management | 0 | 0 | 0 |  | Hoang | Hien | [5 empty] | #DIV/0! | Ignore | In-house | No clear merit & process
| 36 | PROC | MCS | Proc-21 | Add "pull signal for 1 set kitting TV line" on MCS portal | Quality management | Management | 0 | 0 | 0 |  | Hoang | Hien | 1 | 1 | 1.2 | #DIV/0! |  | #DIV/0! | Ignore | In-house | No clear merit & process
| 37 | PSCD | SCS | PS-5 | Shipment status, shiment link | Quality management | Management | 0 | 1.32 | 0 | 0 | Linh | Hien | 3 | 1 | 3.6 | 2.7273 | 9 | 6.8182 | Consider | In-house
| 38 | HR/GA | ALL |  | Checksheet less management Leave, OT, Bus, Guest | Quality management | Management | 1 | 35 | 0 |  | Hoa | Hien | 6 | 1 | 7.2 | 0.20571 | 18 | 0.51429 | Need | In-house
| 39 | PMD |  |  | PMD Production Data Visualization Make plan, Count result qty, Auto input R3 | Quality management | Management | 1 | 6 | 12 | 2 | Hien | Hien | 4 | 1 | 4.8 | 2.8 | 12 | 4 | Consider | In-house
| 40 | PMD |  |  | PMD resin apply improvement Injection production, input location, scan qty, location, visualize, samling checking, e-stock, supply | Quality management | Management | 0 | 0 | 0 | 0 | Khang Trang | Hien | [5 empty] | #DIV/0! | Ignore | In-house | No clear merit & process
| 41 | PMD |  |  | PMD resin apply improvement Kitting: manual search location, wite paper, input data to PC, SAP | Quality management | Management | 0 | 0 | 0 | 0 | Tien | Hien | [5 empty] | #DIV/0! | Ignore | In-house | No clear merit & process
| 42 | ACD/PUS/PE/FE |  |  | Issue material In Out | Quality management | Management | 0 | 0 | 0 |  | Hoa | Hien | 3 | 1 | 3.6 |  | 9 | #DIV/0! | Consider | In-house | New procedure from Procurement, other dept go-live
A | 43 | PROC | MCS | Proc-22 | Changing kitting and supply process material for OLED TV | Quality management | Management | 0 | 0 | 0 |  | Hoang | Hien
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only develop fee. Not include Management fee
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Man-Month: 3K

## Detai Schedule (hidden)
|  |  |  | Jun-22 |  |  |  | Jul-22 |  |  |  | Aug-22 |  |  |  | Sep-22 |  |  |  | Oct-22 |  |  |  | Nov-22 |  |  |  | Dec-22 |  |  |  | Jan-23 |  |  |  | Feb-23 |  |  |  | Mar-23
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Lam | 3 | PUS, PSCD | Shipping advice analysis | Jun-22 W1: Testing SA analysis & adjust program; Sep-22 W1: Develop Analysis and Vendor confirmation; Oct-22 W1: Test; Oct-22 W4: Golive
Lam & New | 3 | PUS, PSCD | Forecast report | Oct-22 W2: Studying; Oct-22 W4: collect data & make FS; Nov-22 W2: develop; Dec-22 W3: Testing; Jan-23 W2: Adjust; Jan-23 W4: Golive
SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Jun-22 W1: Collect SAP data (New Packing/invoice); Jun-22 W4: Collect data outside SAP (VN names, Unit); Jul-22 W3: request/ response to FPT; Aug-22 W1: - Test call API - PSNM active HTTP - Install certificates; Aug-22 W3: Golive